## Summary
Generation Capacity and Transmission Elements Status of CONTD4 and FTC as on date | [6 empty] | check
Total Capacity(MW) Under CONTD4 study
Region | Source (Type) | Total Capacity(MW) | CONTD4 expected to be completed in Mar'26 | CONTD4 expected to be completed in April'26 | CONTD4 expected to be completed in May'26 | CONTD4 expected to be completed in June'26
NR | Wind | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Solar | 3066 | 250 | 250 | 550 | 1400 | -616 | 3066 | 250 | #NAME? | #NAME?
| BESS | 190 | 50 | 50 | 0 | 0 | -90 | 190 | 50 | #NAME? | #NAME?
| Hybrid(Wind+Solar) | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Hybrid(Solar+BESS) | 300 | 100 | 100 | 200 | 281 | 381 | 300 | 100 | #NAME? | #NAME?
| Hybrid(Wind+Solar+BESS) | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Total | 3556 | 400 | 400 | 750 | 1681 | -325 | #NAME? | #NAME? | #NAME? | #NAME?
WR | Wind | 2644.4 | 170 | 456 | 111.8 | 584 | -1322.6 | 2834.4 | 150 | #NAME? | #NAME?
| Solar | 4181.2 | 1020 | 1730 | 200 | 1250 | 18.8 | 5244.2 | 1020 | #NAME? | #NAME?
| BESS | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Hybrid(Wind+Solar) | 659.8 | 150 | 740.8 | 0 | 0 | 231 | 659.8 | 150 | #NAME? | #NAME?
| Hybrid(Solar+BESS) | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Hybrid(Wind+Solar+BESS) | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Total | 7485.4 | 1340 | 2926.8 | 311.8 | 1834 | -1072.8 | #NAME? | #NAME? | #NAME? | #NAME?
SR | Wind | 1689 | 115 | 859 | 0 | 50 | -665 | 1689 | 115 | #NAME? | #NAME?
| Solar | 1246 | 276 | 600 | 100 | 100 | -170 | 1246 | 276 | #NAME? | #NAME?
| BESS | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Hybrid(Wind+Solar) | 710.6 | 134 | 190 | 0 | 207 | -179.6 | 1000.6 | 134 | #NAME? | #NAME?
| Hybrid(Solar+BESS) | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | #NAME? | #NAME?
| Hybrid(Wind+Solar+BESS) | 1639 | 0 | 684 | 0 | 435 | -520 | 1639 | 0 | #NAME? | #NAME?
| Total | 5284.6 | 525 | 2333 | 100 | 792 | -1534.6 | #NAME? | #NAME? | #NAME? | #NAME?
All India | Wind | 4333.4 | 285 | 1315 | 111.8 | 634 | -1987.6
| Solar | 8493.2 | 1546 | 2580 | 850 | 2750 | -767.2
| BESS | 190 | 50 | 50 | 0 | 0 | -90
| Hybrid(Wind+Solar) | 1370.4 | 284 | 930.8 | 0 | 207 | 51.4
| Hybrid(Solar+BESS) | 300 | 100 | 100 | 200 | 281 | 381
| Hybrid(Wind+Solar+BESS) | 1639 | 0 | 684 | 0 | 435 | -520
| Total | 16326 | 2265 | 5659.8 | 1161.8 | 4307 | -2932.4
Total Generation Capacity Details Under FTC/TOC/COD (MW) as on 24-04-26 (Region-wise) | [29 empty] | Change from Previous day
Region | Source (Type) | Total Installed Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity applied for FTC | FTC approved | FTC Pending | TOC Issued | TOC Pending | COD Completed | COD Pending | Expected Capacity(MW) to be commissioned by End of April'26 |  | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | FTC completed | FTC Pending | TOC Completed | TOC Pending | COD Completed | COD Pending | Expected Capacity(MW) to be commissioned in Mar'26 | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | FTC completed | FTC Pending | TOC Completed | TOC Pending | COD Completed | COD Pending | Expected Capacity(MW) to be commissioned in Mar'26 | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | FTC completed | FTC Pending | TOC Completed | TOC Pending | COD Completed | COD Pending | Expected Capacity(MW) to be commissioned in Mar'26 | RANK
NR | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Solar | 4060 | 4054.8 | 2676.22 | 2643.9 | 328.32 | 1801.8 | 0 | 1801.8 | 0 | 1654.6 |  | 4060 | 4054.8 | 2676.22 | 2643.9 | 328.32 | 1801.8 | 0 | 1801.8 | 0 | 1654.6 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| BESS | 850 | 835 | 594.522 | 594.522 | 0 | 591.174 | 0 | 591.174 | 0 | 243.491 |  | 850 | 835 | 594.522 | 594.522 | 0 | 591.174 | 0 | 591.174 | 0 | 243.491 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Hybrid | 870 | 485 | 520 | 620 | 0 | 520 | 0 | 520 | 0 | 187 |  | 870 | 485 | 520 | 620 | 0 | 520 | 0 | 520 | 0 | 187 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Coal | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 660 |  | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 660 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Hydro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| PSP | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 |  | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Total | 7440 | 7034.8 | 5450.742 | 5518.422 | 988.32 | 3912.974 | 0 | 3912.974 | 0 | 2745.091 |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
WR | Wind | 2768.3 | 1386.3 | 1064.9 | 925.4 | 85.95 | 734 | 66 | 726.2 | 2.3 | 510.5 |  | 2768.3 | 1386.3 | 1064.9 | 925.4 | 85.95 | 734 | 66 | 726.2 | 2.3 | 510.5 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Solar | 6040 | 4700 | 5339.76 | 4764.76 | 405 | 4435 | 265 | 4410 | 25 | 1129.76 |  | 6040 | 4700 | 5339.76 | 4764.76 | 405 | 4435 | 265 | 4410 | 25 | 1129.76 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| BESS | 1266 | 1234 | 1280 | 1080 | 200 | 800 | 280 | 800 | 0 | 390 |  | 1266 | 1234 | 1280 | 1080 | 200 | 800 | 280 | 800 | 0 | 390 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Hybrid | 1802.8 | 967.3 | 891.65 | 654.7 | 155.7 | 640.925 | 0 | 640.925 | 0 | 219.475 |  | 1802.8 | 967.3 | 891.65 | 654.7 | 155.7 | 640.925 | 0 | 640.925 | 0 | 219.475 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hydro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| PSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Total | 11877.1 | 8287.6 | 8576.31 | 7424.86 | 846.65 | 6609.925 | 611 | 6577.125 | 27.3 | 2249.735 |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
SR | Wind | 489 | 412 | 298.2 | 298.2 | 0 | 231.3 | 39.9 | 231.3 | 0 | 39.9 |  | 489 | 412 | 298.2 | 298.2 | 0 | 231.3 | 39.9 | 231.3 | 0 | 39.9 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Solar | 916.3 | 776 | 796.1 | 796.1 | 0 | 641.3 | 154.8 | 0 | 0 | 207.6 |  | 916.3 | 776 | 796.1 | 796.1 | 0 | 641.3 | 154.8 | 0 | 0 | 207.6 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hybrid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hydro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| PSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Total | 1405.3 | 1188 | 1094.3 | 1094.3 | 0 | 872.6 | 194.7 | 231.3 | 0 | 247.5 |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
ER | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hybrid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Coal | 2400 | 2400 | 2400 | 1600 | 800 | 800 | 800 | 800 | 0 | 800 |  | 2400 | 2400 | 2400 | 1600 | 800 | 800 | 800 | 800 | 0 | 800 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| Hydro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| PSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Total | 2400 | 2400 | 2400 | 1600 | 800 | 800 | 800 | 800 | 0 | 800 |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
NER | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hybrid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Hydro | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 |  | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
| PSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 0
| Total | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1
All India | Wind | 3257.3 | 1798.3 | 1363.1 | 1223.6 | 85.95 | 965.3 | 105.9 | 957.5 | 2.3 | 550.4 | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| Solar | 11016.3 | 9530.8 | 8812.08 | 8204.76 | 733.32 | 6878.1 | 419.8 | 6211.8 | 25 | 2991.96 | Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| BESS | 2116 | 2069 | 1874.522 | 1674.522 | 200 | 1391.174 | 280 | 1391.174 | 0 | 633.491 | BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| Hybrid | 2672.8 | 1452.3 | 1411.65 | 1274.7 | 155.7 | 1160.925 | 0 | 1160.925 | 0 | 406.475 | Hybrid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| Coal | 3060 | 3060 | 3060 | 2260 | 1460 | 800 | 800 | 800 | 0 | 1460 | Coal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| Hydro | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 | Hydro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| PSP | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 | PSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
| Total | 25122.4 | 20910.4 | 18521.352 | 16387.582 | 2884.97 | 12945.499 | 1605.7 | 12271.399 | 27.3 | 6292.326 | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 1
Transmisision Elements details of FTC
Region | Transmission Element | FTC completed in Mar'26 |  | FTC Pending |  | Commissioing to be completed in Mar'26
|  | ckt km/MVA | Total No | ckt km/MVA | Total No | ckt km/MVA | Total No
NR | Transmission Line _RE Pocket | 158.96 | 4 | 634.68 | 2 | 0 | 0 |  | 158.96 | 4 | 634.68 | 2 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Transmission Line _Not RE Pocket | 381.4 | 3 | 0 | 0 | 0 | 0 |  | 381.4 | 3 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_RE Pocket | 1500 | 1 | 0 | 0 | 1500 | 1 |  | 1500 | 1 | 0 | 0 | 1500 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_Non RE Pocket | 1000 | 2 | 0 | 0 | 0 | 0 |  | 1000 | 2 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
WR | Transmission Line _RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Transmission Line _Not RE Pocket | 679 | 5 | 167.95 | 5 | 536.95 | 9 |  | 679 | 5 | 167.95 | 5 | 536.95 | 9 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_Non RE Pocket | 2816 | 4 | 816 | 2 | 3131 | 5 |  | 2816 | 4 | 816 | 2 | 3131 | 5 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
SR | Transmission Line _RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Transmission Line _Not RE Pocket | 790.496 | 10 | 0 | 0 | 701.08 | 7 |  | 790.496 | 10 | 0 | 0 | 701.08 | 7 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_Non RE Pocket | 4000 | 5 | 0 | 0 | 500 | 1 |  | 4000 | 5 | 0 | 0 | 500 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
ER | Transmission Line _RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Transmission Line _Non RE Pocket | 94.225 | 1 | 0 | 0 | 94.225 | 1 |  | 94.225 | 1 | 0 | 0 | 94.225 | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_Non RE Pocket | 630 | 2 | 0 | 0 | 0 | 0 |  | 630 | 2 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
NER | Transmission Line _RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Transmission Line _Non RE Pocket | 0 | 0 | 97.23 | 6 | 97.23 | 6 |  | 0 | 0 | 97.23 | 6 | 97.23 | 6 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| ICT(MVA)_Non RE Pocket | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
All India | Transmission Line _RE Pocket | 158.96 | 4 | 634.68 | 2 | 0 | 0
| Transmission Line _Not RE Pocket | 1945.121 | 19 | 265.18 | 11 | 1429.485 | 23
| ICT(MVA)_RE Pocket | 1500 | 1 | 0 | 0 | 1500 | 1
| ICT(MVA)_Non RE Pocket | 8446 | 13 | 816 | 2 | 3631 | 6
Total hybrid Capacity Details Under FTC/TOC/COD (MW) as on 24-04-26 | [29 empty] | Change from Previous day
Region | Source (Type) |  | Total Capacity(MW) |  | Capacity applied for FTC | FTC approved | TOC Issued |  | COD Completed | Expected Capacity(MW) to be commissioned by End of April'26 |  |  |  | Total Capacity(MW) |  | Capacity applied for FTC | FTC approved | TOC Completed |  | COD Completed | Expected Capacity(MW) to be commissioned by End of Mar'26
NR | Hybrid(Solar+wind) | Solar | 114.4 |  | 114.4 | 114.4 | 114.4 |  | 114.4 | 0 |  | 0 |  | 114.4 |  | 114.4 | 114.4 | 114.4 |  | 114.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wind | 40.95 |  | 40.95 | 40.4 | 40.4 |  | 40.4 | 0 |  | 0.55 |  | 40.95 |  | 40.95 | 40.4 | 40.4 |  | 40.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hybrid(Solar+wind+BESS) | Solar | 285 |  | 285 | 185 | 88 |  | 88 | 97 |  | 100 |  | 285 |  | 285 | 185 | 88 |  | 88 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wind | 250 |  | 250 | 0 | 0 |  | 0 | 0 |  | 250 |  | 250 |  | 250 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BESS | 180 |  | 180 | 180 | 90 |  | 90 | 90 |  | 0 |  | 180 |  | 180 | 180 | 90 |  | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Solar |  | 399.4 | 0 | 399.4 | 299.4 | 202.4 | 0 | 202.4 | 97
| Total Wind |  | 290.95 | 0 | 290.95 | 40.4 | 40.4 | 0 | 40.4 | 0
| Total BESS |  | 180 | 0 | 180 | 180 | 90 | 0 | 90 | 90
| Grand Total |  | 870.35 | 0 | 870.35 | 519.8 | 332.8 | 0 | 332.8 | 187
WR | Hybrid(Solar+wind) | Solar | 598.4 |  | 33 | 292.9 | 279.125 |  | 279.125 | 46.775 |  | 272.5 |  | 598.4 |  | 33 | 292.9 | 279.125 |  | 279.125 | 46.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wind | 975.4 |  | 122.7 | 361.8 | 361.8 |  | 345.6 | 93 |  | 536.8 |  | 975.4 |  | 122.7 | 361.8 | 361.8 |  | 345.6 | 93 | 0 | 0 | 0 | -9.6634e-13 | -9.6634e-13 | 0 | 0 | 0
| Hybrid(Solar+wind+BESS) | Solar | 50 |  | 0 | 41.65 | 0 |  | 0 | 0 |  | 50 |  | 50 |  | 0 | 41.65 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wind | 175 |  | 0 | 39.6 | 0 |  | 0 | 0 |  | 175 |  | 175 |  | 0 | 39.6 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BESS | 4 |  | 0 | 0 | 0 |  | 0 | 0 |  | 4 |  | 4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Solar |  | 648.4 | 0 | 33 | 334.55 | 279.125 | 0 | 279.125 | 46.775
| Total Wind |  | 1150.4 | 0 | 122.7 | 401.4 | 361.8 | 0 | 345.6 | 93
| Total BESS |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total |  | 1802.8 | 0 | 155.7 | 735.95 | 640.925 | 0 | 624.725 | 181
SR | Hybrid(Solar+wind) | Solar | 395.8 |  | 372.655 | 372.655 | 338.28 |  | 338.28 | 0 |  | #VALUE! |  | #N/A |  | #N/A | #N/A | #N/A |  | #N/A | #N/A | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE!
|  | Wind | 639 |  | 538.52 | 469.22 | 455.36 |  | 455.36 | 83.16 |  | 103.78 |  | 639 |  | 535.22 | 535.22 | 455.36 |  | 455.36 | 79.86 | 0 | 0 | -3.3 | 66 | 0 | 0 | 0 | -3.3
| Hybrid(Solar+PSP) | Solar | 1500 |  | 264 | 249.425 | 249.425 |  | 249.425 | 0 |  | 1250.575 |  | 1500 |  | 545.6 | 545.6 | 249.425 |  | 249.425 | 0 | 0 | 0 | 281.6 | 296.175 | 0 | 0 | 0 | 0
|  | PSP | 1680 |  | 1680 | 1680 | 1680 |  | 1274.825 | 0 |  | #VALUE! |  | #N/A |  | #N/A | #N/A | #N/A |  | #N/A | #N/A | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE!
| Total Solar |  | 1895.8 | 0 | 636.655 | 622.08 | 587.705 | 0 | 587.705 | 0
| Total Wind |  | 639 | 0 | 538.52 | 469.22 | 455.36 | 0 | 455.36 | 83.16
| Total PSP |  | 1680 | 0 | 1680 | 1680 | 1680 | 0 | 1274.825 | 0
| Grand Total |  | 4214.8 |  | 2855.175 |  | 2723.065 |  | 2317.89 | 83.16
All India | Total Solar |  | 2943.6 | 0 | 1069.055 | 1256.03 | 1069.23 | 0 | 1069.23 | 143.775
| Total Wind |  | 2080.35 | 0 | 952.17 | 911.02 | 857.56 | 0 | 841.36 | 176.16
| Total BESS |  | 184 | 0 | 180 | 180 | 90 | 0 | 90 | 90
| Total PSP |  | 1680 |  | 1680 |  | 1680 |  | 1274.825 | 0
| Grand Total |  | 6887.95 |  | 3881.225 |  | 3696.79 |  | 3275.415 | 479
Total Generation Capacity Details Under FTC/TOC/COD (MW) as on 24-04-26 (Source-wise)
Source (Type) | Region | Total Installed Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity applied for FTC | FTC approved | FTC Pending | TOC Issued | TOC Pending | COD Completed | COD Pending | Expected Capacity(MW) to be commissioned by End of April'26 |  | Rank
Wind | NR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| WR | 2768.3 | 1386.3 | 1064.9 | 925.4 | 85.95 | 734 | 66 | 726.2 | 2.3 | 510.5 |  | 1
| SR | 489 | 412 | 298.2 | 298.2 | 0 | 231.3 | 39.9 | 231.3 | 0 | 39.9 |  | 1
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 3257.3 | 1798.3 | 1363.1 | 1223.6 | 85.95 | 965.3 | 105.9 | 957.5 | 2.3 | 550.4 |  | 1
Solar | NR | 4060 | 4054.8 | 2676.22 | 2643.9 | 328.32 | 1801.8 | 0 | 1801.8 | 0 | 1654.6 |  | 1
| WR | 6040 | 4700 | 5339.76 | 4764.76 | 405 | 4435 | 265 | 4410 | 25 | 1129.76 |  | 1
| SR | 916.3 | 776 | 796.1 | 796.1 | 0 | 641.3 | 154.8 | 0 | 0 | 207.6 |  | 1
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 11016.3 | 9530.8 | 8812.08 | 8204.76 | 733.32 | 6878.1 | 419.8 | 6211.8 | 25 | 2991.96 |  | 1
BESS | NR | 850 | 835 | 594.522 | 594.522 | 0 | 591.174 | 0 | 591.174 | 0 | 243.491 |  | 1
| WR | 1266 | 1234 | 1280 | 1080 | 200 | 800 | 280 | 800 | 0 | 390 |  | 1
| SR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 2116 | 2069 | 1874.522 | 1674.522 | 200 | 1391.174 | 280 | 1391.174 | 0 | 633.491 |  | 1
Hybrid | NR | 870 | 485 | 520 | 620 | 0 | 520 | 0 | 520 | 0 | 187 |  | 1
| WR | 1802.8 | 967.3 | 891.65 | 654.7 | 155.7 | 640.925 | 0 | 640.925 | 0 | 219.475 |  | 1
| SR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 2672.8 | 1452.3 | 1411.65 | 1274.7 | 155.7 | 1160.925 | 0 | 1160.925 | 0 | 406.475 |  | 1
Coal | NR | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 660 |  | 1
| WR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| SR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ER | 2400 | 2400 | 2400 | 1600 | 800 | 800 | 800 | 800 | 0 | 800 |  | 1
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 3060 | 3060 | 3060 | 2260 | 1460 | 800 | 800 | 800 | 0 | 1460 |  | 1
Hydro | NR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| WR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| SR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 |  | 1
| All India | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 |  | 1
PSP | NR | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 |  | 1
| WR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| SR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| ER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| NER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| All India | 1000 | 1000 | 1000 | 1000 | 0 | 1000 | 0 | 1000 | 0 | 0 |  | 1
All Sources | NR | 7440 | 7034.8 | 5450.742 | 5518.422 | 988.32 | 3912.974 | 0 | 3912.974 | 0 | 2745.091 |  | 1
| WR | 11877.1 | 8287.6 | 8576.31 | 7424.86 | 846.65 | 6609.925 | 611 | 6577.125 | 27.3 | 2249.735 |  | 1
| SR | 1405.3 | 1188 | 1094.3 | 1094.3 | 0 | 872.6 | 194.7 | 231.3 | 0 | 247.5 |  | 1
| ER | 2400 | 2400 | 2400 | 1600 | 800 | 800 | 800 | 800 | 0 | 800 |  | 1
| NER | 2000 | 2000 | 1000 | 750 | 250 | 750 | 0 | 750 | 0 | 250 |  | 1
| All India | 25122.4 | 20910.4 | 18521.352 | 16387.582 | 2884.97 | 12945.499 | 1605.7 | 12271.399 | 27.3 | 6292.326 |  | 1
COD declared Capacity(MW) in April
Source | NR | WR | SR | ER | NER
Wind | 0 | 3.3 | 0 | 0 | 0
Solar | 435.5 | 441.67 | 46.15 | 0 | 0
BESS | 246.366 | 360 | 0 | 0 | 0
Hybrid | 180 - BESS 114.4 - Solar 40.95 - Wind | 16.2 - Wind | 0 | 0 | 0
Coal | 0 | 0 | 0 | 0 | 0
Hydro | 0 | 0 | 0 | 0 | 0
PSP | 250 | 0 | 0 | 0 | 0
Total | 1177.216 | 821.17 | 46.15 | 0 | 0

## NR
Generation Capacity Under Process of CONTD-4
Sr. No | Generating Station | Pooling Station | Region | Generation Type (Wind/Solar/Hybrid/BESS/Coal/Hydro etc) | Capacity(MW) | Application Date (dd-mm-yyyy) | Proposed FTC date | Capacity(MW) to be completed in Apr'26 | Issues if any causing delay/Remark
1 | TP SAURYA LIMITED | BIKANER-III | NR | Hybrid Solar(361MVA+BESS 72MVA) | 300 | 23-01-2026 | April'26 | 100 | Under Process (Final Grant is yet to be approved by CTUIL for BESS)
2 | SOLTOWN INFRA PRIVATE LIMITED | Bikaner-II | NR | Solar | 325 | 2025-05-08 | April'26 | 125 | Meeting held on 22.04.2026 for expeditiously closing the CONN-TD-4
3 | NTPC RENEWABLE ENERGY LIMITED(Kalasar-1) | BIKANER-III | NR | Solar | 250 | 2025-02-10 | April'26 | 125 | Review of Study Completed, Under Finalization, compliance sheet will be shared shortly
4 | NTPC RENEWABLE ENERGY LIMITED(Kalasar-2) | BIKANER-III | NR | Solar | 250 | 2025-06-10 | May'26 | 0 | Review of Study Completed, Under Finalization, compliance sheet will be shared shortly
5 | Serentica Renewables India Private Ltd | Bikaner-II | NR | BESS | 50 | 2026-12-03 | April'26 | 50 | Reply pending at plant end
6 | Serentica Renewables India Private Ltd | Bikaner-II | NR | Solar | 141 | 24-03-2026 | June'26 | 0 | Final Grant given for 281 MW (Solar + BESSS) in existing 180 MW SRI4L project at Bikaner-II PS
|  |  |  | BESS | 140
7 | Sunbreeze Renewables Nine Pvt Ltd | BIKANER-III | NR | Solar | 1400 | 15-12-2025 | June'26 | 0 | Compliance sheet already shared (Closed)
8 | Hazel Hybren Private Ltd | Bikaner-IV | NR | Solar | 300 | 31-09-2025 | Nov'26 | 0 | Under Process
9 | Litsolaire Energy Private Ltd | Bikaner-II | NR | Solar | 100 | 20-01-2026 | May'26 | 0 | Under Process
10 | Furies Solren Private Ltd | Bikaner-IV | NR | Solar | 300 | 30-12-2025 | Dec'26 | 0 | Reply pending at plant end. Models & reports not submitted.
Sr. No | Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Total Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Other remark |  |  |  |  | FTC Pending (formula) | COD Pending (Formual)
1 | IB VOGT SOLAR SEVEN PRIVATE LIMITED(IBVSSPL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.03.2026 18.03.2026 | 200 | 27.03.2026 | 200 | 150MW (30.03.2026) 50MW (01.04.2026) |  | 0 | 0 | 0 | 100 | [5 empty] | 0 | 0 | 0
2 | RENEW SAMIR SHAKTI THREE PRIVATE LIMITED | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.02.2026 16.02.2026 | 300 | 210.31MW dated17.03.2026 64.67MW dated 24.03.2026 25.02 MW 31.03.2026 | 300 | 210.31MW dated 17.03.2026 64.67MW dated 26.03.2026 |  | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0
3 | RENEW SOLAR SHAKTI THREE PRIVATE LIMITED(RSS3PL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 2026-11-02 | 300 | 2026-11-03 | 300 | 2026-03-13 |  | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0
4 | ADANI SOLAR ENERGY BARMER ONE LIMITED(ASEB1L)) | Fatehgarh-III | Solar | NR | 600 | 600 | 251 | SOLAR | 251 | 2026-03-15 | 251 | 23-03-2026 | 251 | 25.03.2025 |  | 0 | 0 | 0 | 0 | [5 empty] | 349 | 0 | 0
5 | Khaba Renewable Energy Private Limited (KREPL) | Fatehgarh-III | Solar | NR | 250 | 250 | 221 | SOLAR | 221 | 2026-02-03 | 150 | 100MW on 13-03-26 50 MW on 27-03-2026 | 150 | 100MW-14 Mar 26 50MW-27 Mar 26 |  | 0 | 0 | 0 | 71 | [5 empty] | 29 | 0 | 0
6 | Juniper Green Stellar Private Limited(JGSPL) | Fatehgarh-IV | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) | NR | 715 | 365 | 365 | SOLAR+BESS | 465 | Solar:16.03.2026 (185MW) 06.04.2026 (100MW) BESS: 17.03.2026 (90MW) 21.03.2026 (90 MW) | 365 | 88MW solar-25.03.26 90MW-BESS 02-04-2026 10.04.2026 (97 MW Solar) 90MW BESS 22.04.2026 | 365 | 27 Mar 26-88MW solar 12.04.26 97MW Solar 90MW BESS-08.04.2026 90MW BESS 24.04.2026 |  | 0 | 0 | 0 | 187 |  | Capacity(MW) applied for FTC_ Solar- 185 BESS-180 | TOC Isuued capcity: 88-solar 90MW-BESS | COD Declared capcity: 88-solar 90MW-BESS | Capacity(MW) commisioning expected in Apr'26: (187)solar-97 Bess-90 | 163 | -100 | 0
7 | PROJECT ELEVEN RENEWABLE POWER PRIVATE LIMITED(P11RPPL) | Bhadla-II | Solar | NR | 150 | 150 | 100 | SOLAR | 100 | 25-03-2026 | 87.5 | 17.04.2025 | 87.5 | 21.04.2026 |  | 0 |  | 0 | 62.5 | [5 empty] | 0 | 0 | 0
8 | PROJECT 16 RENEWABLE POWER PRIVATE LIMITED(P16RPPL) | Bhadla-II | Solar | NR | 300 | 300 | 200 | SOLAR | 200 | 25-03-2026 | 150 | 16.04.2026 | 150 | 18.04.2026 |  | 0 |  | 0 | 50 | [5 empty] | 100 | 0 | 0
9 | ACME SUN POWER PRIVATE LIMITED(ASPPL) | Bhadla-II | BESS | NR | 300 | 300 | 166.665 | BESS | 166.665 | 66.66 FTC completed on 26-02-2026. 33.33 MW 17 MAR 26 66.66MW 24-03-2026 33.33MW | 166.665 | 33.335 MW 06-03-2026 33.335 MW 12-03-2026 33.33MW- 31.03.2026 33.33MW- 01.04.2026 33.334MW-06.04.2026 | 166.665 | 33.335 MW on 08-03-2026 33.335 MW on 14-03-2026 33.333 MW on 02-04-2026 33.333 MW on 03-04-2026 33.334 MWon 08-04-2026 |  | 0 |  | 0 | 133 | [5 empty] | 0.335 | 0 | 0
10 | ACME SURYODAYA PRIVATE LIMITED(ACME_SPL) | Fatehgarh-I | BESS | NR | 300 | 285 | 285 | BESS | 285 | 76 MW FTC completed on 10-02-2026. 95 MW FTC APPROVED 14 MAR 2026 114 MW FTC issued on 29-03-2026 | 285 | 19 MW 25-02-2026 38 MW 03-03-2026 19 MW11-03-2026 95MW-23.03.2026 76MW-06.04.2026 | 285 | 19 MW on 27-02-2026 38 MW on 05-03-2026 19 MW on 13-03-2026 95 MW on 25-03-2026 76 MW on 08-04-2026 38MW on 13-04-2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 15 | 0 | 0
11 | ACME Surya POWER Private Limited (ASRPPL) | Bikaner-II | BESS | NR | 250 | 250 | 142.857 | BESS | 142.857 | 16-03-2026 (71.43MW) 17-03-2026 (35.71MW) 24-03-2026 (35.71MW) | 139.509 | 23-03-2026 (60MW) 24-03-2026 (35.71MW) 29-03-2026 (11.429MW) | 139.509 | 60MW dated 23.03.26 35.714 dated 24-03-26 11.429 MW on 29-03-26 32.366MW on 13-04-26 |  | 0 | 0 | 0 | 110.491 | [5 empty] | 0 | 0 | 0
12 | Clean Max Celestial Private Limited(CMCPL) | Bikaner-II | Solar | NR | 250 | 250 | 234.57 | SOLAR | 0 | NA | [5 empty] | 234.57 |  | 0 | 250 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 234.57 | 0
13 | Clean Max Enviro Energy Solutions Limited(CMEESL) | Bikaner-II | Solar | NR | 100 | 100 | 93.75 | SOLAR | 0 | NA | [5 empty] | 93.75 |  | 0 | 100 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 93.75 | 0
14 | Energizent POWER Private Limited | Fatehgarh-III | Solar | NR | 250 | 250 | 129.6 | SOLAR | 129.6 | 60.6 MW on 27-03-2026 69 MW on 29-10-2025 | 69 | 2025-07-11 | 69 | 2025-09-11 |  | 0 |  | 0 | 60.6 | [5 empty] | 120.4 | 0 | 0
15 | BBMB Panipat | Panipat | Solar | NR | 10 | 8.8 | 8.8 | SOLAR | 8.8 | 2026-02-03 | 8.8 | 2026-11-03 | 8.8 | 2026-11-03 |  | 0 |  | 0 | 0 | [5 empty] | 1.2 | 0 | 0
16 | Tehri | - | Pump Storage | NR | 1000 | 1000 | 1000 | PSP HYDRO | 1000 | 2026-06-03 | 1000 | 250 MW U#4 on 10.04.2026 | 1000 | 12.04.2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
17 | Adani Green Energy Twenty Five B Limited (AGE25BL) | Ramgarh-II | Solar | NR | 500 | 500 | 137.5 | SOLAR | 137.5 | 23-03-2026 | 137.5 | 28-03-2026 | 137.5 | 30-03-2026 |  | 0 |  | 0 | 362.5 | [5 empty] | 0 | 0 | 0
18 | Teq Green POWER XVIII Private Limited | Fatehgarh-III | Solar | NR | 50 | 50 | 0 | SOLAR | 0 | [6 empty] | 0 |  | 0 | 50 |  | FTC yet to apply for FTC |  |  |  | 0 | 0 | 0
19 | Renew Solar Shakti Five Private Limited | Fatehgarh-III | Solar | NR | 400 | 400 | 400 | SOLAR | 400 | 200MW on 25-03-2026 200MW on 28-03-2026 | [5 empty] | 0 |  | 0 | 400 |  | Annexure B returb 24.03.26 |  |  |  | 0 | 0 | 0
20 | AMPIN ENERGY GREEN TEN PRIVATE LIMITED(AEG10PL) | Fatehgarh-IV | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) | NR | 155 | 120 | 155 | solar+Wind | 155 | 2026-12-02 | 155 | 27.03.2026 | 155 | 114.4MW--04.04.2026 40.4MW- 04.04.2026 |  | 0 |  |  |  |  | TOC Isuued capcity: 120(solar-114.4+wind-40.4) |  |  |  | 0 | 0 | 0
21 | HRP Green POWER Private Limited | Bhadla-III | Solar | NR | 300 | 296 | 0 | SOLAR | 296 | 2026-01-04 | 148 | 13.04.2026 | 148 | 148MW 13.04.2026 |  | 0 |  | 0 | 148 | [5 empty] | 4 | -296 | 0
22 | Aditya Birla Renewables subsdiary Ltd | Fatehgarh-III | Hybrid_(292MVA Solar, 287MVA Wind) | NR | 608 not applied | 608 not applied | 0 | Solar+Wind | 0 | [6 empty] | 0 |  | 0 | 608 not applied | Hybrid_(292MVA Solar, 287MVA Wind) | Registration and Conn6 pending |  |  |  | #VALUE! | 0 | 0
23 | Ghatampur TPS | Ghatampur | Thermal | NR | 660 | 660 | 660 | Thermal | 660 | 30-03-2026 | [5 empty] | 660 |  |  | 660 | [5 empty] | 0
Sr. No | Transmission Elements Under Process of FTC
| Agency/Owner | Name of Line/ICT /GT/ST | Type (Line/ICT /GT/ST) | RE/Non-RE | Voltage Rating (kV) | Capacity (MVA) | Line length | Date of First Time Energization & Integration | Pendig for FTC (Yes/No) | Proposed FTC date if Pending | Capacity (MVA) to be commissioned in Apr'26 | Line Length (ckt km) to be commissioned in Apr'26 | Reason for delay/Any Otherremark
1 | FATEHGARH III BEAWAR TRANSMISSION LIMITED(F3BTL) | 765kV Fatehgarh_III(PG)-BEAWAR-Ckt1 at Beawar2 | Line | RE | 765 |  | 317.34 |  | Yes |  |  |  | Annexure-B returned 30.03.26
2 | FATEHGARH III BEAWAR TRANSMISSION LIMITED(F3BTL) | 765kV Fatehgarh_III(PG)-BEAWAR-Ckt2 at Beawar2 | Line | RE | 765 |  | 317.34 |  | Yes |  |  |  | Annexure-B returned 30.03.26
3 | POWERGRID Bikaner Neemrana Transmission Limited(PBNTL) | 400 KV Bikaner Bikaner_III ckt1 (LILO of 400 KV Bikaner Bikaner_II) | Line | RE | 400 |  | 39.93 | FTC issued on 19.03.2026 | No |  |  |  | Charged on 01:50hrs 26.03.26
4 | POWERGRID Bikaner Neemrana Transmission Limited(PBNTL) | 400 KV Bikaner Bikaner_III ckt2 (LILO of 400 KV Bikaner Bikaner_II) | Line | RE | 400 |  | 39.93 | FTC issued on 19.03.2026 | No |  |  |  | Charged on 02:17hrs 26.03.26
5 | POWERGRID Bikaner Neemrana Transmission Limited(PBNTL) | 400 KV Bikaner_II Bikaner_III ckt3 (LILO of 400 KV Bikaner Bikaner_II) | Line | RE | 400 |  | 39.55 | FTC issued on 19.03.2026 | No |  |  |  | Charged on 02:12hrs 26.03.26
6 | POWERGRID Bikaner Neemrana Transmission Limited(PBNTL) | 400 KV Bikaner_II Bikaner_III ckt4 (LILO of 400 KV Bikaner Bikaner_II) | Line | RE | 400 |  | 39.55 | FTC issued on 19.03.2026 | No |  |  |  | Charged on 01:38hrs 26.03.26
7 | UPPTCL | ICT-1 AT 400 KV GARAUTHA | ICT | Non-RE | 400 | 500 |  | 18-03-2026 | No |  |  |  | FTC issued
8 | PSTCL | ICT 2 at Behman Jassa Singh (PSTCL). | ICT | Non-RE | 400 | 500 |  | 17.03.2026 | No |  |  |  | FTC issued
9 | 1500 MVA ICT-1 Bikaner-III S/S | ICT--1 | ICT | RE | 765/400 | 1500 |  |  | No |  | 1500 |  | FTC issued
10 | POWERGRID | 765 kV Dausa-Phagi ckt-2 (LILO of 765 kV Gwalior-Phagi-2) | Line | Non-RE | 765 |  | 281.4 | 2026-06-03 | No |  | 0
11 | HVPNL | 220kV Bhiwani (PG) - Isherwal Ckt-1 | Line | Non-RE | 220 |  | 50 | FTC issued 25.03.2026 | No |  | 0
12 | HVPNL | 220kV Bhiwani (PG) - Isherwal Ckt-2 | Line | Non-RE | 220 |  | 50 | FTC issued 25.03.2026 | No |  | 0
13 | UPPTCL | 400KV GARAUTHA-ORAI(UP) LINE.(after LILO OF 400KV ORAI(PG)-ORAI CKT-I AT 400 KV S/S GARAUTHA )( | Line | Non-RE | 400 |  | 92.05 | 17.03.2026 | No |  | 0
14 | BEAWAR TRANSMISSION LIMITED(BTL) | 400kV BEAWAR-Merta(RS)-1 (After LILO of 400kV Kota-Merta Line-01 at Beawar(BTL) | Line | RE | 400 |  | 79.71 |  | yes |  |  |  | Annex-B under process
15 | BEAWAR TRANSMISSION LIMITED(BTL) | 400kV BEAWAR-Kota(PG)-1( After LILO of 400kV Kota-Merta Line at Beawar(BTL) | Line | RE | 400 |  | 241.84 |  | yes |  |  |  | Annex-B under process
16 | BEAWAR TRANSMISSION LIMITED(BTL) | 765/400/33kV, 1500 MVA, 3x1-Phase, ICT - 1 at BEAWAR | ICT | RE | 765 | 1500 |  |  | Yes |  |  |  | Annex=B applied on 29.03.2026
Sr. No |  | Source wise Segregation of hybrid Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark
1 | Juniper Green Stellar Private Limited(JGSPL) | Fatehgarh-IV | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) | NR | 285 | 365 | 185 | Solar | 185 | Solar:16.03.2026 (185MW) | 88 | 88MW solar-25.03.26 | 88 | 27 Mar 26-88MW solar |  | 0 | 0 | 0 | 97
|  |  | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) |  | 250 |  | 0 | Wind | 0
|  |  | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) |  | 180 |  | 180 | BESS | 180 | BESS: 17.03.2026 (90MW) 21.03.2026 (90 MW) | 90 | 90MW-BESS 02-04-2026 | 90 | 90MW BESS-04.04.2026 |  |  |  |  | 90
2 | AMPIN ENERGY GREEN TEN PRIVATE LIMITED(AEG10PL) | Fatehgarh-IV | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) | NR | 114.4 | 120 | 114.4 | Solar | 114.4 | 2026-12-02 | 114.4 | 27.03.2026 | 114.4 | 114.4MW--04.04.2026 |  | 0 |  | 114.4 | 0
|  |  | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) |  | 40.95 |  | 40.4 | Wind | 40.4 |  | 40.4 | 31.03.2026 | 40.4 | 40.4MW- 04.04.2026
20 | AMPIN ENERGY GREEN TEN PRIVATE LIMITED(AEG10PL) | Fatehgarh-IV | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) | NR | 155 | 120(solar-114.4+wind-40.4) | 120(solar-114.4+wind-40.4) | solar+Wind | 120(solar-114.4+wind-40.4) | 2026-12-02 | 120(solar-114.4+wind-40.4) | 27.03.2026 |  |  |  | 0 |  | 114.4 | 0 |  | TOC Isuued capcity: 120(solar-114.4+wind-40.4) |  |  |  | #VALUE! | #VALUE! | #VALUE!

## WR
Sr. No |  | Generation Capacity Under Process of CONTD-4
| Name of Developer | Generating Station | Pooling Station | Region | Generation Type (Wind/Solar/Hybrid/BESS/Coal/Hydro etc) | Capacity(MW) | Application Date | Proposed FTC date | Capacity(MW) to be completed in Apr'26 | Issues if any causing delay/Remark
1 | JUNIPER GREEN ENERGY LIMITED | Ran JGEPL | Jamkhambaliya | WR | Wind | 60 | 17-02-2025 | Apr'26 | 0 | 1. Technical details of the WTG, SVG, and PPC are pending.
2 | MOUNTING RENEWABLE POWER LIMITED | Tebhada | Jamkhambaliya | WR | Hybrid (Wind- 161.7 MW + Solar-99 MW) | 250 | 17-09-2025 | Apr'26 | 100 | The complaince sheet is signed
3 | REWA ULTRA MEGA SOLAR LIMITED (SPD: Waree) | Badi | Neemuch PS | WR | Solar | 170 | 17-11-2025 | Apr'26 | 170 | The complaince sheet is signed
4 | GUJARAT INDUSTRIES POWER COMPANY LTD (SPD: Sterling & Wilson Renewable Energy Limited) | GSECL SBPS (Interim for GSECL NBPS) | Khavda-2 PS | WR | Solar | 500 | 2026-12-03 | Apr'26 | 500 | The complaince sheet is signed
5 | GUJARAT INDUSTRIES POWER COMPANY LTD (SPD: SAEL, COAL INDIA) | GIPCL PSS1 | Khavda-2 PS | Khavda-2 PS | Solar | 600 | 24-02-2026 | Apr'26 | 300 | Revised PSCAD models are awaited from developer
6 | AIRPOWER WINDFARMS PRIVATE LIMITED | Sidhpur | Jamkhambaliya | WR | Hybrid (Wind - 291 MW + Solar - 50 MW) | 175 | 2026-03-03 | Apr'26 | 50 | The complaince sheet is signed
7 | Continuum POWER Trading (TN) Pvt. Ltd. & Oyster Green Hybrid One Private Limited | Dayapar | Bhuj PS | WR | Wind | 135 | 26-08-2025 | Apr'26 | 50 | CAT-2 signed. FTC application is awaited. The 50 MW capacity is ready. CEA inspection is expected by 30.04.2026
8 | NTPC RENEWABLE ENERGY LIMITED | Jamjhodpur | Jamhambaliya | WR | Wind | 280 | 29-10-2025 | Apr'26 | 50 | Revised PSCAD models are awaited from developer
9 | VEH JAYIN RENEWABLES PRIVATE LIMITED | Dhar | Rajgarh PG | WR | Hybrid (Wind - 151.8 MW + Solar - 45.1 MW) | 151.8 | 23-12-2025 | Apr'26 | 0 | Revised PSCAD models are awaited from developer
10 | NTPC RENEWABLE ENERGY LIMITED | Vanki Devsar | Bhuj PS | WR | Wind | 165 | 19-03-2026 | Apr'26 | 50 | CAT-II is signed for 157 MW as per CEA directives for allowing standalone study acceptance for the capacity ready up to Jun'26
11 | NTPC REL | Samanda | Bhuj-II PS | WR | Wind | 98 | 14-07-2025 | 30-06-2026 | 0 | The connection agreement has been signed for 102 MW
12 | Adani Green Energy Limited | KPSS7 | Khavda-1 PS | WR | Solar | 1050 | 26-11-2025 | 31-06-2026 | 0 | Revised PSCAD models are awaited from developer. Application closed by CTUIL.
13 | ADANI GREEN ENERGY THIRTY TWO LIMITED | Mandovi | Bhuj-II PS | WR | Wind | 225.5 | 15-07-2025 | 30-06-2026 | 0 | Revised PSCAD models are awaited from developer
14 | ADANI WIND ENERGY KUTCHH THREE LIMITED | Navinal | Navinal | WR | Wind | 260.5 | 15-07-2025 | 30-06-2026 | 0 | Revised PSCAD models are awaited from developer
15 | Abnergia Renewable Private Limited (ARPL) / Oyster RENEWABLE ENERGY PVT LTD | Agar Malwa | Pachora PS | WR | Hybrid (81 MW Wind+100 MW Solar) | 33 | 26-08-2025 | 31-03-2026 | 0 | The connection agreement has been signed for 81 MW Connection agreement for 33 MW Solar capacity Under GNA 5.2 is awaited
16 | TATA POWER RENEWABLE ENERGY LIMITED | Borkhed | Kallam PS | WR | Wind | 111.6 | 20-08-2025 | 2026-03-05 | 0 | Revised PSCAD models are awaited from developer
17 | Ayana Renewable POWER Four Pvt. Ld. (ARP4PL) & Seven Renewable POWER Private Limited | Devsar | Bhuj-1 PS | WR | Hybrid (Solar-37.5 MW Wind- 112.5 MW) | 50 | 26-12-2024 | 15-01-2026 | 0 | The connection agreement has been signed for 100 MW 1. ICT overloading for the complete 150 MW capacity is to be addressed.
18 | SPRING VAYU VIDYUT PRIVATE LIMITED | Bharadwa | Radhanesda PS | WR | Solar | 218 | 2025-09-10 | 31-06-2026 | 50 | Revised PSCAD models are awaited from developer
19 | NHPC | NHPC PSS-1 | Khavda-3 PS | WR | Solar | 600 | 24-10-2025 | 31-12-2026 | 0 | Incomplete submission 1. Technical details of the inverter, SVG, and PPC are pending. 2. ICT overloading is observed beyond nameplate rating (up to 112%) in reactive POWER capability studies. 3. PSSE/PSCAD models can be reviewed only after receipt of pending unit-level technical details.
20 | Sprng Vayu Vidyut Private Limited | Hajaratpur | Rajgarh PG | WR | Wind | 151.8 | 19-11-2025 | 31-12-2026 | 0 | The connection agreement has been signed for 165 MW 1. The reactive POWER capability study is not as per plant's operating philosophy, WTG terminal voltages are beyond the nominal rating. 2. Model improvement in PSCAD to be addressed. (Faster initialization, longer simulation run). Timeline will be included in the compliance sheet.
21 | Serentica Renewables India Private Limited | Konhali | Solapur PG | WR | Wind | 250 | 2025-09-10 | - | 0 | Incomplete submission: 1. PSSE and PSCAD model submission is pending
22 | ReNew Samir Urja Private Limited & Renew Urja Sanchar Ltd | Badnagar | Indore PG | WR | Wind | 600 | 2025-02-12 | 30-09-2026 | 0 | Pending points: 1. Reactive POWER capability study cases not submitted. 2. Revised PSCAD models are awaited from developer
23 | GUJARAT INDUSTRIES POWER COMPANY LTD | GIPCL PSS2 | Khavda-2 PS | WR | Solar | 500 | 2025-12-12 | 31-04-2026 | 0 | Incomplete submission: 1. Harmonic simulation model not submitted 2. Reactive POWER capability study models not submitted 3. Revised PSCAD models are awaited from developer
24 | INDIANOIL NTPC GREEN ENERGY PRIVATE LIMITED | Manja | Jamkhambaliya | WR | Wind | 147 | - | 19-11-2026 | 0 | Technical data submission is pending
25 | ADANI RENEWABLE ENERGY EIGHT LIMITED | Ludbay | Bhuj-II PS | WR | Solar | 150 | 2026-11-01 | 30-06-2026 | 0 | Pending points: 1. PSCAD model initialisation and slow run issues to be addressed 2. FFR response to be modeled properly 3. Difference in PSSE and PSCAD response to be resolved
26 | Skadar Solar Pvt. Ltd. | Skadar Solar Pvt. Ltd. | Solapur PS | WR | Solar | 200 | 2026-11-01 | 31-05-2026 | 0 | Incomplete submission: 1. PSCAD models not submitted
27 | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | SOLARCRAFT POWER INDIA 16 PRIVATE LIMITED | Solapur PS | WR | Solar | 211.2 | 2026-02-03 | 18-12-2026 | 0 | Revised PSCAD models are awaited from developer
28 | Avaada Energy Private Limited | Avaada Energy Private Limited | Jamkhambaliya | WR | Wind | 200 | 2026-02-03 | 31-08-2026 | 0 | Revised PSCAD models are awaited from developer
29 | NTPC RENEWABLE ENERGY LIMITED | NTPC REL PSS4 | Khavda-2 PS | WR | Solar | 795 | 03.03.2026 |  | 0 | Revised PSCAD models are awaited from developer
30 | Serentica Renewables India Private Limited | Dahiphal | Kallam PS | WR | Wind | 150 | 03.04.2026 |  | 0 | Revised PSCAD models are awaited from developer
31 | Sprng Power Earth Pvt. Ltd. (SPEPL) | Padan | Radhanesda PS | WR | Solar | 250 | 23.03.2026 |  | 0 | Revised PSCAD models are awaited from developer
32
Sr. No |  | Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC approval date | TOC Issued Capacity(MW) | TOC issuance date | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  | FTC pending (Formula) | COD Pending (Formula)
1 | AGE26AL Khavda PSS6 | KPS1 | Solar | WR | 750 | 750 | 750 | Solar | 750 | 2026-04-14 | 750 | 2026-04-20 | 750 | 50: 25-01-2026 250: 15-03-2026 50: 21-03-2026 50: 29-03-2026 50: 16-04-2026 58: 01-04-2026 242: 20-04-2026 |  | 0 | 0 | 0 | 0 | CEA EI approval yet to be received | Full COD complete | 0 | 0 | 0
2 | ASEJ6PL Khavda PSS8 | KPS3 | Wind | WR | 62.4 | 62.4 | 62.4 | Wind | 62.4 | 2026-03-06 | 62.4 | 2026-03-28 | 62.4 | 2026-03-28 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
3 | AGE25CL Khavda PSS8 | KPS3 | Solar | WR | 500 | 500 | 500 | Solar | 500 | 2026-03-27 | 375 | 2026-03-30 | 350 | 2026-03-30 |  | 0 | 125 | 25 | 150 |  |  | 0 | 0 | 25
4 | AGE24L SRPL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-03-13 | 100 | 2026-03-25 | 100 | 2026-03-26 |  | 0 | 50 | 0 | 50 |  |  | 0 | 0 | 0
5 | AGE24L Khavda PSS5 | KPS1 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-02-16 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
6 | AGE26BL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-02-16 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
7 | AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) | WR | 298 | 216 | 298 | Hybrid | 298 | 2026-03-09 | 298 | 2026-03-17 | 298 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Hybrid connectivity 216 MW Full COD complete | 0 | 0 | 0
8 | ARE43L BESS - SRPL Khavda PSS10 | KPS3 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 2026-03-16 | 400 | 2026-04-15 | 400 | 80: 11-03-2026 80: 20-03-2026 60: 28-03-2026 120: 30-03-2026 20: 02-04-2026 20: 11-04-2026 20: 15-04-2026 |  | 80 | 0 | 0 | 75 |  |  | 0 | 80 | 0
9 | AGE26AL - SRPL Khavda PSS12 | KPS3 | Wind | WR | 140.4 | 137.5 | 140.4 | Wind | 140.4 | 2026-03-12 | 140.4 | 2026-03-20 | 137.5 | 2026-03-22 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.9 | 0 | 2.9
10 | ARE37L BESS - AGEL Khavda PSS5 | KPS1 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 2026-04-10 | 320 | 2026-04-17 | 320 | 80: 01-04-2026 80: 01-04-2026 80: 11-04-2026 60: 15-04-2026 20: 17-04-2026 |  | 80 | 80 | 0 | 155 |  |  | 0 | 80 | 0
11 | Renew Green MHS One Pvt Ltd - RGESPL PSS-1 | Solapur | Wind | WR | 181.5 | 181.5 | 181.5 | Wind | 161.7 | 2026-03-06 | 161.7 | 2026-03-26 | 161.7 | 2026-03-27 |  | 19.8 | 0 | 0 | 19.8 |  |  | 0 | 19.8 | 0
12 | Avaada GJ Sustainable Private Limited | Lakadiya | Solar | WR | 200 | 200 | 200 | Solar | 200 | 2026-03-24 | 200 | 2026-04-07 | 200 | 108.33: 07-02-2026 91.67: 11-04-2026 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
13 | Veh Saurya Urja Pvt Ltd | Pachora | Wind | WR | 163.2 | 81.9 | 81.9 | Wind | 81.9 | 2026-02-23 | 69.3 | 2026-03-25 | 69.3 | 2026-03-26 |  | 0 | 0 | 0 | 0 |  |  | -93.9 | 0 | 0
14 | Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) | WR | 181 | 67 | 52.8 | Solar | 52.8 | 2026-02-25 | 52.8 | 2026-03-25 | 52.8 | 2026-03-26 |  | 0 | 0 | 0 | 0 |  |  | -128.2 | 0 | 0
15 | Juniper Green Energy Limited | Jam Khambhaliya | Wind | WR | 300 | 100 | 0 | Wind | 0 | [6 empty] | 0 |  | 0 | 100 | Wind FTC application yet to be submitted | PSS FTC - protection coordination pending from site, hence protection consent is remaining | -200 | 0 | 0
16 | Sprng Akshay Urja Pvt Ltd | Rajgarh | Wind | WR | 167.2 | 165 | 165 | Wind | 165 | 2026-01-13 | 165 | 2026-04-08 | 162.7 | 100: 29-12-2025 16.5: 31-12-2025 6.6: 05-01-2026 6.6: 28-01-2026 13.2: 30-01-2026 6.6: 04-02-2026 9.9: 18-02-2026 3.3: 10-04-2026 |  | 0 | 0 | 2.3 | 3.3 |  |  | -1.2 | 0 | 2.3
17 | TEQ Green Power XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) | WR | 204.1 | 150.3 | 201 | Hybrid | 174 | 2026-04-22 | 160.225 | 2026-04-01 | 160.225 | Wind: 18.9: 30-06-2025 32.4: 30-06-2025 13.5: 16-08-2025 13.5: 02-10-2025 2.7: 07-11-2025 5.4: 29-11-2025 10.8: 20-12-2025 16.2: 03-04-2026 Solar: 24.425: 16-08-2025 22.4: 11-01-2026 |  | 27 | 0 | 0 | 40.775 |  |  | -3.1 | 27 | 0
18 | Ayana Power Four Private Limited at Devasar | Bhuj | Hybrid (Solar + Wind) | WR | 129.9 | 100 | 129.9 | Hybrid | 129.9 | 2025-07-10 | 129.9 | 2026-03-31 | 129.9 | 2026-03-31 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
19 | Ayana Power Four Private Limited at Zura | Bhuj | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-03-17 | 150 | 2026-03-31 | 150 | 2026-03-31 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
20 | NTPC REL Khavda PSS2 | KPS2 | Solar | WR | 1555 | 1555 | 1555 | Solar | 1555 | 2026-03-23 | 1555 | 2026-03-30 | 1555 | 2026-03-30 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 | 0 | 0
21 | NTPC REL Khavda PSS1 | KPS3 | Solar | WR | 1200 | 1095 | 1200 | Solar | 1095 | 2026-04-11 | 1005 | 2026-03-30 | 1005 | 2026-03-30 |  | 105 | 90 | 0 | 195 | CONN-TD-4 remaining for 105 MW |  | 0 | 105 | 0
22 | NTPC REL Vanki | Bhuj | Wind | WR | 165 | 0 | 116.55 | Wind | 50.4 | 2026-04-20 | [5 empty] | 66.15 |  | 0 | 50.4 |  | Combined with lead generator Ayana | -114.6 | 66.15 | 0
23 | Coal India Limited at GIPCL | KPS2 | Solar | WR | 300 | 0 | 300 | Solar | 0 | [6 empty] | 300 |  | 0 | 0 | CAT-2 yet to be received | POWER park developer GIPCL - proposed in April | -300 | 300 | 0
24 | NTPC REL at GSECL | KPS2 | Solar | WR | 265 | 0 | 64.76 | Solar | 64.76 | 2026-04-21 | [5 empty] | 0 |  | 0 | 64.76 |  | POWER park developer GSECL | -200.24 | 0 | 0
25 | Engie Energy India Pvt Ltd at GSECL | KPS2 | Solar | WR | 200 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 200 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS - proposed in April | 0 | 0 | 0
26 | JSW Renew Energy Ten Ltd at GSECL | KPS2 | Solar | WR | 300 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 300 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS already commuincated through mail for submission of FTC application but it is stiil not received as on 27.03.26 | 0 | 0 | 0
27 | Mounting Renewable Power Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) | WR | 250 | 0 | 128.7 | Hybrid | [7 empty] | 128.7 | 0 | 0 | 128.7 | CAT-2 yet to be received |  | -121.3 | 128.7 | 0
28 | Serentica Renewables India4 Pvt Ltd | Kallam | Wind | WR | 350 | 250 | 66 | Wind | 66 | 2026-03-31 | [5 empty] | 0 | 66 | 0 | 66 |  |  | -284 | 0 | 0
29 | Airpower Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind+BESS) | WR | 229 | 140 | 81.25 | Hybrid | [7 empty] | 0 |  | 0 | 50 |  |  | -179 | 81.25 | 0
30 | Oyster Green Hybrid One Pvt Ltd at Dayapar | Bhuj | Wind | WR | 99 | 99 | 0 | Wind | [7 empty] | 0 |  | 0 | 0 |  | FTC application yet to be submitted for Wind - proposed in April | -99 | 0 | 0
31 | ARE36L BESS - AGEL Khavda PSS8 | KPS3 | BESS | WR | 316 | 284 | 320 | BESS | 280 | 2026-04-24 | 80 | 2026-04-23 | 80 | 2026-04-24 |  | 40 | 200 | 0 | 160 |  |  | -76 | 40 | 0
32 | AGE25CL Khavda PSS14 | KPS3 | Wind | WR | 67.6 | 65 | 67.6 | Wind | 67.6 | 2026-03-25 | 67.6 | 2026-03-28 | 65 | 2026-03-28 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.6 | 0 | 2.6
33 | AGE26AL Khavda PSS14 | KPS3 | Wind | WR | 208 | 208 | 130 | Wind | 130 | 2026-04-13 | 67.6 | 2026-04-22 | 67.6 | 2026-04-22 |  | 0 |  | 0 | 130 |  |  | -10.4 | 0 | 0
34 | NTPC REL at Jamjodhpur | Jam Khambhaliya | Wind | WR | 630 | 0 | 53.55 | Wind | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received |  | -630 | 53.55 | 0
35 | Veh Jayin Renewables Private Limited | Rajgarh | Hybrid (Solar + Wind) | WR | 196.8 | 0 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in April | -196.8 | 0 | 0
36 | Continuum Power Trading (TN) Private Limited | Bhuj | Wind | WR | 36 | 36 | 0 | Wind | [7 empty] | 0 |  | 0 | 36 |  | FTC application yet to be submitted for Wind - proposed in April | 0 | 0 | 0
37 | Aditya Birla Renewable Energy Limited (ABREL) Valsara | Bhuj-II | Hybrid (Solar + Wind) | WR | 314 | 294 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CONN-TD-4 signed, CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in May | -314 | 0 | 0
38 | Waree Energies Limited | Rewa | Solar | WR | 170 | 0 | 170 | Solar | [10 empty] | 170 | CAT-2 yet to be received
39 | Sprng Vayu Vidyut Pvt Ltd | Rajgarh | Wind | WR | 198 | 0 | 0 | Wind | [10 empty] | 105 | CAT-2 yet to be received
[18 empty] | Total | 2249.735
Sr. No |  | Transmission Elements Under Process of FTC
| Agency/Owner | Name of Line/ICT /GT/ST | Type (Line/ICT /GT/ST) | RE/Non-RE | Voltage Rating (kV) | Capacity (MVA) | Line length | Date of First Time Energization & Integration | Pendig for FTC (Yes/No) | Proposed FTC date if Pending | Capacity (MVA) to be commissioned in Apr'26 | Line Length (ckt km) to be commissioned in Apr'26 | Reason for delay/Any Otherremark
1 | CSPTCL | 220kV Bhatapara CG-Bhatapara PG-2 anti-theft from bhatapara CG | Line | Non-RE | 220 |  | 5.4 |  | Yes |  | 0 | 5.4 | PTCC Approval pending, EI expired on 24-03-2026. Under review
2 | CSPTCL | 220kV Bhatapara CG-Bhatapara PG-3 anti-theft from bhatapara CG | Line | Non-RE | 220 |  | 5.4 |  | Yes |  | 0 | 5.4 | PTCC Approval pending, EI expired on 24-03-2026. Under review
3 | CSPTCL | 220kV Raipur pool-Kawardha(Gendpur)-D/C | Line | Non-RE | 220 |  | 59 |  | Yes |  | 0 | 59 | Application yet to be received. As informed by CSPTCL PTCC is pending
4 | GETCO | 400KV Vadavi-Charal line-2 | Line | Non-RE | 400 |  | 92.3 |  | Yes |  | 0 | 92.3 | Non submission of Board Resolution approval for interim arrangement. GETCO informed that they are planning to charge in original configuration by doing LILO of 400kV Halvad (Mansar)-Vadavi at Charal by 31-03-2026
5 | GETCO | 400/220 kV ICT-3 at Veloda | ICT | Non-RE | 400 | 315 |  | ICT idle charged from 400kV Side on 22:14/30.03.2026 | No |  | 315 | 0
6 | GETCO | 400kV Bus reactor at Hadala | BR | Non-RE | 400 | 125 |  |  | Yes |  | 125 | 0 | Protection review, EI Approval pending. Under review | 1728
7 | GETCO | 400kV Shapar-Pachham-D/C | Line | Non-RE | 400 |  | 100 | Ckt-1: 17:15/24.03.2026 Ckt-2: 19:26/24.03.2026 | No |  | 0 | 100
8 | GETCO | 400kV Bus reactor at Asoj | BR | Non-RE | 400 |  | 125 | 13:24/27.03.2026 | No |  | 125
9 | MPPTCL | 400/220 kV ICT-4 at Bina MP | ICT | Non-RE | 400 | 315 |  |  | Yes |  | 315 | 0 | EI Approval, SACADA p2p testing, Protection review,Study review pending. Under review | 1737
10 | MPPTCL | 400kV LILO of Damoh-Bhopal at Sagar without 50 MVAR LR on Sagar-Bhopal | Line | Non-RE | 400 |  | 19 | 17:15/20-03-2026 | No |  | 0 | 19 | Charged without 50 MVAR LR
11 | MSETCL | 400kV Bableshwar-Kudus-D/C anti-theft from Kudus | Line | Non-RE | 400 |  | 21 | Line proposed for anti theft charging on 27-03-2026. Full charging of lines by 31-03-2026 | No |  | 0 | 21
11 | MSETCL | 400kV Bableshwar-Kudus-D/C | Line | Non-RE | 400 |  | 229 |  | No |  | 0 | 229 |  | 1834
12 | MSETCL | 400/220kV Nanded ICT-3 | ICT | Non-RE | 400 | 501 |  | 20:57/31.03.2026 | No |  | 501 | 0 |  | 1806
13 | MSETCL | Jejuri 400/220kV ICT-4 | ICT | Non-RE | 400 | 501 |  |  | Yes |  |  | 500 | EI Approval , Protection settings confirmation, loadability limit pending. Under review | 1820, 1821
14 | MSETCL | 220kV Nashik-Navsari line-2 LILO at Deosane SS | Line | Non-RE | 220 |  | 5.85 |  | Yes |  |  | 5.85 | Navsari-Deosane charge on 24-03-2026. Nasik Navsari SCADA pending | 1785
15 | MSETCL | 400kV Deepnagar-Waluj line-1 line length increase from 125 kms to 310 kms | Line | Non-RE | 400 |  | 310 |  | No |  | 310 |  | Partial LILO at Taptitanda charging of the line till loc. 181 | 1761
16 | POWERGRID | 400/220 kV ICT-4 at Satna PG | ICT | Non-RE | 400 | 500 |  | ICT idle charged from 400kV Side on 00:09/30.03.2026 | No |  | 500 | 0
17 | POWERGRID | 765/400kV ICT-3 at New Navsari | ICT | Non-RE | 765 | 1500 |  | 20:11/31.03.2026 | No |  | 1500 | 0 |  | 1722
18 | POWERGRID | 765/400kV ICT-4 at Padghe | ICT | Non-RE | 765 | 1500 |  |  | Yes | 15-04-2026 | 1500 | 0 | Application yet to be received
19 | POWERGRID | 765kV New Navsari-Padghe-D/C | Line | Non-RE | 765 |  | 225 | Ckt-1: 06:27/27-03-2026, Ckt-2: 23:58/27.03.2026 | No |  | 0 | 225
20 | POWERGRID | 400kV New Navsari-Kala-D/C | Line | Non-RE | 400 |  | 260 | Ckt-2: 00:51/02.04.2026 | No |  | 0 | 260 |  | 1809
21 | Powergrid KPS3 Transmission Limited | 400kV main and tie bays of 765kV ICT-4 & PSS-12 | Bays | Non-RE | 400 |  |  |  | Yes |  | 0 | 0 | SCADA pending. Under review
22 | Powergrid KPS3 Transmission Limited | KPS3 ICT-4 | ICT | RE | 765 | 1500 |  |  | Yes | 31-03-2026 | 1500 |  | SCADA review, Protection reveiew, metering dummy data pending | 1791
23 | Pachora POWER Transmission Limited | 400kV Ujjain-Pachora-D/C | Line | RE | 400 |  | 59 |  | Yes | 2026-10-04 |  | 59 | EI, PTCC Pending, SCADA p2p testing, protection review, study review pending, Meter details & meter data of Ujjain end pending. Under review | 1778
24 | Pachora POWER Transmission Limited | 3 nos. 400/220kV ICTs at Pachora | ICT | RE | 400 | 500 |  |  | Yes | 2026-10-04 | 500 |  | EI, PTCC Pending, SCADA p2p testing, protection review, study review, Meter data pending. Under review | 1778
25 | Khavda IVA | 400 kV 12 nos. bays at KPS3 | Bays | RE | 400 |  |  |  | Yes |  | 0 | 0 | 4 bays cleared. 8 bays SCADA p2p testing pending. Under review | 1759
Sr. No |  | Source wise Segregation of hybrid Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC approved | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark
6 | AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) - 216 MW hybrid connectivity | WR | 142 | 216 | 0 | Solar | 142 | 2026-02-17 | 142 | 2026-03-17 | 142 | 2026-03-20 | 0 | 0 | 0 | 0 | 0
| AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) - 216 MW hybrid connectivity | WR | 156 |  | 0 | Wind | 156 | 2026-03-13 | 156 | 2026-03-17 | 156 | 2026-03-20 | 0 | 0 | 0 | 0 | 0
13 | Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) - 181 MW hybrid connectivity | WR | 100 | 181 | 0 | Solar | 52.8 | 2026-02-25 | 52.8 | 2026-03-25 | 52.8 | 2026-03-26 | 0 | 0 | 0 | 0 | 0
| Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) - 181 MW hybrid connectivity | WR | 81 |  | 0 | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | FTC application yet to be received for wind, plant not ready yet
16 | TEQ Green POWER XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) - 150.3 MW hybrid connectivity | WR | 55.6 | 150.3 | 0 | Solar | 60.6 | 2026-04-22 | 46.825 | 2026-01-09 | 46.825 | 2026-01-11 | 2026-03-25 | 0 | 0 | 0 | 13.775
| TEQ Green POWER XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) - 150.3 MW hybrid connectivity | WR | 148.5 |  | 27 | Wind | 113.4 | 2026-03-27 | 113.4 | 2026-04-01 | 97.2 | 2025-12-20 | 2026-03-25 | 27 | 0 | 0 | 27 | right of way issues were reported at site | infirm injection extension permission from Hon'ble CERC is sought by agency for 10.8 MW wind
24 | Mounting Renewable POWER Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) - 250 MW hybrid connectivity | WR | 88.3 | 0 | 33 | Solar | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-25 | 33 | 0 | 0 | 33 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar
| Mounting Renewable POWER Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) - 250 MW hybrid connectivity | WR | 161.7 |  | 95.7 | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-25 | 95.7 | 0 | 0 | 66 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar
26 | AirPOWER Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind + BESS) - 175 MW hybrid connectivity | WR | 50 | 50 | 0 | Solar | 41.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar, BESS. Proposed for April 2026
| AirPOWER Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind + BESS) - 175 MW hybrid connectivity | WR | 175 | 90 | 0 | Wind | 39.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar, BESS. Proposed for April 2026
| AirPOWER Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind + BESS) - 175 MW hybrid connectivity | WR | 4 | 0 | 0 | BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar, BESS. Proposed for April 2026
35 | Veh Jayin Renewables Private Limited | Rajgarh | Hybrid (Solar + Wind) - 151.8 MW hybrid connectivity | WR | 45 | 0 | 0 | Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar
| Veh Jayin Renewables Private Limited | Rajgarh | Hybrid (Solar + Wind) - 151.8 MW hybrid connectivity | WR | 151.8 |  | 0 | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar
18 | Ayana Power Four Private Limited at Devasar | Bhuj | Hybrid (Solar + Wind) - 100 MW hybrid connectivity | WR | 92.4 | 100 | 0 | Wind | 92.4 | 2025-07-10 | 92.4 | 2026-03-31 | 92.4 | 2026-03-31 | 0 | 0 | 0 | 0 | 0
| Ayana Power Four Private Limited at Devasar | Bhuj | Hybrid (Solar + Wind) - 100 MW hybrid connectivity | WR | 37.5 |  | 0 | Solar | 37.5 | 2025-06-26 | 37.5 | 2025-10-15 | 37.5 | 2025-10-17 | 0 | 0 | 0 | 0 | 0
37 | Aditya Birla Renewable Energy Limited (ABREL) Valsara | Bhuj-II | Hybrid (Solar + Wind) - 314 MW hybrid connectivity | WR | 184 | 294 | 0 | Wind | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar, BESS. Proposed for April 2026
| Aditya Birla Renewable Energy Limited (ABREL) Valsara | Bhuj-II | Hybrid (Solar + Wind) - 314 MW hybrid connectivity | WR | 130 |  | 0 | Solar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar, BESS. Proposed for April 2026

## ER
Sr. No | Generation Capacity Under Process of CONTD-4
| Generating Station | Pooling Station | Region | Generation Type (Wind/Solar/Hybrid/BESS/Coal/Hydro etc) | Capacity(MW) | Application Date | Proposed FTC date | Capacity(MW) to be completed in Apr'26 | Issues if any causing delay/Remark
1
Sr. No | Generation Capacity Under Process for FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | FTC Pending formula | COD Pending Formula
1 | PVUNL Unit-2 | - | Coal | ER | 2400 | 2400 | 2400 | Coal | 1600 | - | 800 | - | 800 | - | - | 800 | 800 | 0 | 800 | SPS has been implemented as per the undertaking submitted. | Format-IV has been issued on 16.03.2026. Trial operation of Unit #2 (800 MW) of Patratu STPP Phase-I (3×800 MW) is tentatively expected from 13.04.2026. | 800 | 0
Sr. No | Transmission Elements Under Process of FTC
| Agency/Owner | Name of Line/ICT /GT/ST | Type (Line/ICT /GT/ST) | RE/Non-RE | Voltage Rating (kV) | Capacity (MVA) | Line length | Date of First Time Energization & Integration | Pendig for FTC (Yes/No) | Proposed FTC date if Pending | Capacity (MVA) to be commissioned in Apr'26 | Line Length (ckt km) to be commissioned in Apr'26 | Reason for delay/Any Otherremark
1 | PGCIL ERTS-I | 400kV Fararkka Kahalgaon Ckt-1 (after reconductoring work) | Line | Non-RE | 400 | - | 94.225 | 17-03-2026 | No |  |  | 94.225
2 | DVC | 400/220/33 kV, 315 MVA ICT-II at Koderma S/S. | ICT | Non-RE | 400/220 | 315 |  | 2026-05-03 | No
3 | PGCIL Odisha Projects | 400/220/33 kV, 315 MVA ICT-I at Jeypore S/S. | ICT | Non-RE | 400/220 | 315 |  | 13-03-2026 | No

## NER
Sr. No | Generation Capacity Under Process of CONTD-4
| Generating Station | Pooling Station | Region | Generation Type (Wind/Solar/Hybrid/BESS/Coal/Hydro etc) | Capacity(MW) | Application Date | Proposed FTC date | Capacity(MW) to be completed in Apr'26 | Issues if any causing delay/Remark
1
Sr. No | Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity (MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity (MW) | FTC date if completed | TOC Issued Capacity (MW) | TOC issuance date if Completed | COD declared Capacity (MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Other remark | FTC Pending fromula | COD Pending formula
1 | Subansiri Lower HEP | - | Hydro | NER | 2000 | 2000 | 1000 | Hydro | 750 | Unit-2: 02.12.2025 Unit-3: 21.01.2026 Unit-1: 31.01.2026 | 750 | Unit-2: 20.12.2025 Unit-3: 30.01.2026 Unit-1: 09.03.2026 | 750 | Unit-2: 23.12.2025 Unit-3: 01.02.2026 Unit-1: 20.03.2026 | Unit-4: 29.04.2026 | 250 |  |  | 250 | Unit-4 FTC application under process |  | 250 | 0
Sr. No | Transmission Elements Under Process of FTC
| Agency/ Owner | Name of Line/ICT /GT/ST | Type (Line/ICT /GT/ST) | RE/Non-RE | Voltage Rating (kV) | Capacity (MVA) | Line length | Date of First Time Energization & Integration | Pendig for FTC (Yes/No) | Proposed FTC date if Pending | Capacity (MVA) to be commissioned in Apr'26 | Line Length (ckt km) to be commissioned in Apr'26 | Reason for delay/Any Otherremark
1 | TSECL | 132 kV SM Nagar ISTS - SM Nagar after reconductoring with HTLS | Line | Non-RE | 132 |  | 10.33 |  | Yes | 30.04.2026 |  | 10.33 | NERPC relay setting approval, Fresh/ Suitable Advisory of PTCC and Manually triggered DR-EL are yet to be submitted
2 | TSECL | 132 kV SM Nagar (ISTS) - Bodhjungnagar after reconductoring with HTLS | Line | Non-RE | 132 |  | 17.93 |  | Yes | 30.04.2026 |  | 17.93 | RIO clearanc, NERPC relay setting approval and Fresh/ Suitable Advisory of PTCC are yet to be submitted
3 | TSECL | 132 kV Kumarghat (PG) - P.K Bari after reconductoring with HTLS | Line | Non-RE | 132 |  | 1.58 |  | Yes | 30.04.2026 |  | 1.58 | NERPC relay setting approval, Fresh/ Suitable Advisory of PTCC and Manually triggered DR-EL are yet to be submitted
4 | TSECL | 132kV PK Bari (ISTS) - Manu line (Reconductoring LILO of 132 kV PK Bari ISTS - Ambassa line at 132 kV Manu) | Line | Non-RE | 132 |  | 10.6 |  | Yes | 30.04.2026 |  | 10.6 | Connectivity Agreement, Relay settings approval from NERPC, Fresh/ Suitable Advisory of PTCC, Compliance with RLDC observations on the OTDR report and SEM data of the meter at Manu end are yet to be submitted.
5 | POWERGRID | 132 kV Melriat (PG) - Zuangtui (Zemabawk) line after HTLS reconductoring with HTLS | Line | Non-RE | 132 |  | 10.19 |  | Yes | 30.04.2026 |  | 10.19 | RIO Clearance, NERPC relay setting approval, Fresh/ Suitable Advisory of PTCC, Relay settings file (.csv & pdf) and Manually triggered DR-EL are yet to be submitted.
6 | AEGCL | 220 kV Sankardevnagar - Lower Kopili HEP line-2 | Line | Non-RE | 220 |  | 46.6 |  | Yes | 30.04.2026 |  | 46.6 | NERPC relay setting approval, Relay settings file (.csv & pdf) and Manually triggered DR-EL are yet to be submitted.

## SR
Sr. No | Generation Capacity Under Process of CONTD-4
| Generating Station | Pooling Station | Region | Generation Type (Wind/Solar/Hybrid/BESS/Coal/Hydro etc) | Capacity(MW) | Application Date | Proposed FTC date | Capacity(MW) to be completed in Apr'26 | Issues if any causing delay/Remark
1 | NHPC | 400/220kV NP Kunta | SR | Solar | 100 | 21-02-2025 | Jun'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models receievd on 06.04.2026 from CTUIL
2 | Zenataris | 400/220kV Hiriyur | SR | Hybrid(Wind+Solar) | 200 | 27-03-2025 | Mar'26 | 134 | Models complied and compliance sheet sent to CTUIL. CONNTD-4 Issued for 200MW on 31.03.2026 for installed capacity of 300.3MW |  |  |  |  | 45
3 | AMPIN | 765/400/220kV Kurnool-III | SR | Hybrid(Wind+Solar) | 150 | 26-02-2026(reapplied after exhausting 3 revisions) | May'26 |  | Revised models received on 09.03.2026,Model check is in progress. |  |  |  | 2026-04-08 | 2026-05-23
4 | AMPIN | 765/400/220kV Kurnool-III | SR | Solar | 100 | 27-08-2025 | May'26 |  | PSCAD & PSSE not complied
5 | KSPDCL | 400/220kV Pavagada | SR | Solar | 300 | 2025-08-09 | Mar'26 |  | Revised models received on 20.03.2026 and model check is in progress
6 | TPREL | 765/400/220kV Koppal-II | SR | Solar | 170 | 2025-09-09 | Sep'26 |  | Compliance sheet sent to CTUIL
7 | ReNew Vikram Shakti Pvt Ltd | 400/220kV Ananthapuram | SR | Hybrid(Wind+Solar+BESS) | 684 | 21-11-2025 | Apr'26 |  | PSCAD dynamic model & PSSE not complied .Revised models received on 31.03.2026
8 | IRCON | 400/220kV Pavagada | SR | Solar | 100 | 17-08-2023 | Mar'26 | 100 | applied for connectivity enhacement,PSCAD dynamic model not complied ,Revised models receievd and observations sent to CTUIL on 01.04.2026
9 | M/s SolarXL Beta Energy Pvt Ltd.(HEXA) | 400/220kV Gadag-II | SR | Hybrid(Wind+Solar) | 207 | 2025-07-12 | Jun'26 |  | PSCAD dynamic model & PSSE not complied .Revised models received on 01.04.2026
10 | JINDAL GREEN WIND 1 PRIVATE LIMITED | 765/400/220kV Koppal-II | SR | Wind | 700 | 31-12-2025 | Mar'26 |  | PSCAD Harmonic, dynamic model & PSSE models not complied .Revised models awaited from developer
11 | PROJECT NINE RENEWABLE POWER PRIVATE LIMITED | 400/220kv Ananthapuram PS | SR | Wind | 295 | 21-01-2026 | May'27 |  | PSCAD dynamic model & PSSE not complied
12 | Ayana Renewable POWER Four Pvt. Ltd. | 400/220kv Ananthapuram PS | SR | Wind | 50 |  | Jun'26 |  | PSCAD dynamic model & PSSE not complied
13 | JSW_270 | 400/230kV Karur | SR | Wind | 120 | 25-12-2025(reapplied after exhausting 3 revisions) | Mar'26 |  | applied for connectivity enhacement ,Models received on 22.03.2026 and Observations sent on 06.04.2026
14 | JSW_150 | 400/230kV Karur | SR | Wind | 55 | 2023-11-03 | Mar'26 | 55 | CONTD-4 issued for enhanced connectivity from 84MW to 136MW on 24.03.2026
15 | Hero Solar Energy Pvt. Ltd. | 765/400/220kV Kurnool-III | SR | Hybrid(Wind+Solar+ BESS) | 135 | 29-01-2026 | Jun'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models awaited from developer
16 | Hero Solar Energy Pvt. Ltd. | 765/400/220kV Kurnool-III | SR | Hybrid(Wind+Solar+ BESS) | 270 | 29-01-2026 | Jul'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models awaited from developer
17 | NTPC Ramagundam | 400/220kV Ramagundam | SR | Solar | 176 | 29-01-2026 | Mar'26 | 176 | Cat-2 signed on 22.03.2026
18 | SECI | 400/220kV Pavagada | SR | Solar | 300 | 28-01-2026 | Mar'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models awaited from developer
19 | TPREL | 765/400/220kV Koppal-II | SR | Wind | 288 | 20-02-2026 | Jul'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models awaited from developer
20 | TPREL | 400/230kV Karur | SR | Wind | 93 | 2026-12-02 | Jul'26 |  | PSCAD dynamic model & PSSE not complied ,Revised models awaited from developer
21 | Hero Solar Energy Pvt. Ltd. | 400/220kV Bidar | SR | Hybrid(Wind+Solar+ BESS) | 300 | 2026-09-03 | Jun'26 |  | Model submitted on 10.03.2026 & Model check in progress
22 | Hero Solar Energy Pvt. Ltd. | 400/220kV Bidar | SR | Hybrid(Wind+Solar+ BESS) | 250 | 2026-09-03 | Dec'26 |  | Model submitted on 10.03.2026 & Model check in progress
23 | RSRPL | 400/220kV Gadag | SR | Wind | 88 | 28-08-2023 | Mar'26 | 60 | Model complied and cat-2 signed on 23.03.2026
24 | Veh Green Energy Private Limited | 765/400/220kV Koppal-II | SR | Hybrid(Wind+Solar) | 153.6 | 27-03-2026 | Sep'26 |  | Models received on 27.03.2026
25 | TPREL | 765/400/220kV Koppal-II | SR | Solar+BESS | 232.5 | 2026-02-04 | Sep'26 |  | Models received on 02.04.2026
26 | JSW_140 | 400/230kV Tuticorin-II | SR | Hybrid(Solar+Wind) | 140 | 2026-08-04 | Sep'26 |  | Models received on 08.04.2026 AND model check is in progress
27 | AMPIN | 400/220kV Bidar | SR | Hybrid(Solar+Wind) | 150 | 2026-10-04 | Sep'26 |  | Models received on 10.04.2026 AND model check is in progress
28 | JSW_Neo | 400/230kV Karur | SR | Wind | 330 | 2026-06-04 | sep'26 |  | Models received on 06.04.2026 AND model check is in progress
Sr. No | Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  | FTC Pending formula | CoD pending formula
1 | SAEL Solar MHP2 Pvt Ltd | Kurnool-III | Solar | SR | 359.7 | 300 | 359.7 | Solar | 359.7 | 26-02-2026 | 359.7 | 13-03-2026 | 300 (359.7) | 09-01-2026 (156.88 MW) , 23-02-2026 ( 66.06 MW) , 13-03-2026 (77.06 MW) |  | 0 |  | 0 |  |  | Total plant commissioned |  | 0 | #VALUE!
2 | Sembcorp Green Infra Pvt. Ltd. | Gadag | Wind | SR | 300 | 262 | 109.2 | Wind | 109.2 | 01-09-2025 , 13-02-2026 , 11-02-2026 | 69.3 |  | 69.3 | 17-01-2025 |  | 0 | 39.9 | 0 | 39.9 |  | ToC for 14.7 MW issued on 23.03.26 |  | 0 | 0
3 | JSW Renew Energy Limited | Karur | Wind | SR | 189 | 150 | 189 | Wind | 189 | 17-09-2025 | 162 |  | 162 | 09.05.25 (32.4MW) 28.03.25 (43.2 MW) 27.03.25 (27 MW) 28.02.25 (59.4 MW) |  | 0 |  | 0 |  |  | Remaining 10 WTG's of 2.7 MW Plant PPC Report to be submitted by Developer but period for infirm injection i.e., 45 days plus 3 months expired . M/s JSW has to approach commission for infirm injection approval. |  | 0 | 0
7 | TP Saurya Limited | Koppal | Solar | SR | 352 | 300 | 281.6 | Solar | 281.6 | 23-03-2026 | 281.6 | 52.8MW: 17.04.26 | 238.46 (281.6) | 08-01-2026 ( 130.77 MW), 03-02-2026 (61.54 MW), 18-04-2026 (46.15MW) |  | 0 | 0 | 0 | 52.8 |  |  |  | 0 | #VALUE!
8 | NTPC Ramagundam (176MW) | Ramagundam | Solar | SR | 204.6 | 176 | 154.8 | Solar | 154.8 | 27-03-2026 |  |  |  | Trial run on 20.04.26 |  | 0 | 154.8 | 0 | 154.8
Sr. No | Transmission Elements Under Process of FTC
| Agency/Owner | Name of Line/ICT /GT/ST | Type (Line/ICT /GT/ST) | RE/Non-RE | Voltage Rating (kV) | Capacity (MVA) | Line length | Date of First Time Energization & Integration Approval | Pendig for FTC (Yes/No) | Proposed FTC date if Pending | Capacity (MVA) to be commissioned in Apr'26 | Line Length (ckt km) to be commissioned in Apr'26 | Reason for delay/Any Otherremark
1 | Gadag IIA Transmission Limited | 400kV Gadag PSS-Koppal PSS 1 | SR | RE | 400kV |  | 49.78 | 2026-02-03 | No
2 | Gadag IIA Transmission Limited | 400kV Gadag PSS-Koppal PSS 2 | SR | RE | 400kV |  | 49.78 | 2026-02-03 | No
3 | Gadag IIA Transmission Limited | 400/220kV ICT 3 at Gadag PSS | SR | RE | 400/220kV | 500 |  | 2026-04-03 | No
4 | Gadag IIA Transmission Limited | 400/220kV ICT 4 at Gadag PSS | SR | RE | 400/220kV | 500 |  | 2026-04-03 | No
5 | Gadag IIA Transmission Limited | 400/220kV ICT 5 at Gadag PSS | SR | RE | 400/220kV | 500 |  | 2026-04-03 | No
6 | Gadag IIA Transmission Limited | 400/220kV ICT 6 at Gadag PSS | SR | RE | 400/220kV | 500 |  | 2026-11-03 | No
7 | TGTRANSCO | 400kV Vattem Uddandapur-1 | Line | Non-RE | 400kV |  | 34.139 | 2026-05-03 | No |  |  |  | Anti Theft Charging from Vattem end
8 | TGTRANSCO | 400kV Vattem Uddandapur-2 | Line | Non-RE | 400kV |  | 34.139 | 2026-05-03 | No |  |  |  | Anti Theft Charging from Vattem end
9 | TANTRANSCO | 100MVA, 400/11.5kV ST 1 at ENNORE SEZ | ST | Non-RE | 400kV | 100 |  | 2026-06-03 | No
10 | TANTRANSCO | 400KV Sholinganallur Taramani-1 | Line | Non-RE | 400kV |  | 21.138 | 13-03-2026 | No |  |  |  | Anti Theft Charging from Sholinganallur end
11 | APTRANSCO | 500MVA 400/220kV ICT 3 at Rachagunneri SS | ICT | Non-RE | 400kV | 500 |  | 24-03-2026 | No |  | 500 | 0
12 | TGTRANSCO | 400kV Maheswaram Uddandapur -1 | Line | Non-RE | 400kV |  | 60.18 | 25-03-2026 | No |  | 0 | 60.18 | Anti Theft Charging from Maheswaram end
13 | TGTRANSCO | 400kV Maheswaram Uddandapur -2 | Line | Non-RE | 400kV |  | 60.18 | 25-03-2026 | No |  | 0 | 60.18 | Anti Theft Charging from Maheswaram end
14 | PGCIL SR1 | 765 KV Maheshwaram SS Line 1 at Kurnool-III (Anti Theft Charging) | Line | Non-RE | 765kV |  | 123.11 | 17-03-2026 | No |  | 0 | 123.11 | Anti Theft Charging from Kurnool-III end
15 | PGCIL SR1 | 765 KV Maheshwaram SS Line 2 at Kurnool-III (Anti Theft Charging) | Line | Non-RE | 765kV |  | 123.11 | 17-03-2026 | No |  | 0 | 123.11 | Anti Theft Charging from Kurnool-III end
16 | PGCIL SR1 | 1500MVA, 765/400kV Maheswaram ICT 3 | ICT | Non-RE | 765/400kV | 1500 |  | 18-03-2026 | No |  |  | 0
17 | PGCIL SR1 | 500MVA, 400/220kV Ananthpuram ICT 3 | ICT | Non-RE | 400/220kV | 500 |  | 23-03-2026 | No |  |  | 0
18 | PGCIL SR1 | 1500MVA, 765/400kV Kurnool (New) ICT 3 | ICT | Non-RE | 765/400kV | 1500 |  | 24-03-2026 | No |  |  | 0
19 | PGCIL SR1 | 765 KV Kurnool-III Line-1 at Maheshwaram SS end (Anti Theft Charging) | Line | Non-RE | 765kV |  | 122.3 | 28-03-2026 | No |  | 0 | 122.3 | Anti Theft Charging from Maheswaram end
20 | PGCIL SR1 | 765 KV Kurnool-III Line-2 at Maheshwaram SS end (Anti Theft Charging) | Line | Non-RE | 765kV |  | 122.3 | 28-03-2026 | No |  | 0 | 122.3 | Anti Theft Charging from Maheswaram end
21 | PGCIL SR1 | 400kV Kadapa Line-1 at Ananthapuram SS end (Anti Theft Charging) | Line | Non-RE | 400kV |  | 89.9 | 28-03-2026 | No |  | 0 | 89.9 | Anti Theft Charging from Ananthapuram end
22 | PGCIL SR1 | 400kV Kadapa Line-2 at Ananthapuram SS end (Anti Theft Charging) | Line | Non-RE | 400kV |  | 89.9 | 29-03-2026 | No |  | 0 | 89.9 | Anti Theft Charging from Ananthapuram end
23 | KPTCL | 220kV Kudgi_NTPC - Savalagi Line 1 | Line | Non-RE | 220kV |  | 64.07 | 30-03-2026 | No |  | 0 | 64.07 | LILO of 220kV KudgiNTPC-Vajramatti at Savalagi
24 | KPTCL | 220kV Kudgi_NTPC - Savalagi Line 2 | Line | Non-RE | 220kV |  | 64.07 | 30-03-2026 | No |  | 0 | 64.07 | LILO of 220kV KudgiNTPC-Vajramatti at Savalagi
25 | PGCIL SR1 | 400 KV/220 KV/33 KV ICT 4 at 400/220kV Ananthpuram SS | ICT | Non-RE | 400 KV/220 KV/33 KV | 500 |  | 30-03-2026 | No |  | 500
26 | TANTRANSCO | 230kV Arasur-Kalivelampatty | Line | Non-RE | 230kV |  | 20.93 | 13-04-2026 | No |  |  | 20.93 | LILO of 230kV Arasur PG -Ingur at Kalivelampatty
26 | TANTRANSCO | 160 MVA, 220/33kV Power Transformer 2 at Zenataris 300.3MW PSS | PT | RE | 220/33kV | 160 |  | 15-04-2026 | No |  | 160
Sr. No | Generation Capacity Under Process of FTC
| Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Apr'26 |  | Issues if any causing delay in FTC/TOC/COD | Any Otherremark
1 | Serentica Renewables India 1 Private Limited | Koppal | Hybrid(wind+Solar) | SR | 204 |  | 195.3 | Wind | 195.3 | 11-02-2026, 12-03-2026 | 195.3 | 10-03-2026, 16-03-2026 | 195.3 | 10-03-2026, 18-03-2026 | [7 empty] | No pending Requests
[5 empty] | 195.8 |  | 191.4 | Solar | 191.4 |  | 191.4 |  | 191.4 | [8 empty] | No pending Requests
2 | Serentica Renewables India 3 Private Limited | Gadag | Hybrid(wind+Solar) | SR | 270 |  | 207.92 | Wind | 207.92 | 26-02-2026 , 10-03-2026, 18-03-2026 | 194.06 | 2026-12-03 | 194.06 | 2026-12-03 |  |  | 13.86 |  | 13.86
[5 empty] | 200 |  | 181.255 | Solar | 181.255 |  | 146.88 | 27-03-2026 | 146.88 | 27-03-2026
3 | Greenko AP01 IREP Pvt Ltd | Kurnool | Hybrid with PSP_Solar | SR | 1500 |  | 545.6 | Solar | 545.6 | 264:10-01-2026 281.6: 22-04-2025 | 249.425 | 14-03-2026 | 249.425 | 18-03-2026 |  |  |  | 0
[5 empty] | 1680 |  | 1680 | PSP | 1680 |  | 1680 |  | 1274.825 | 18-03-2026 |  |  |  | 405.175
4 | Zenataris Renewable Energy Private Limited | Hiriyur | Hybrid(wind+Solar) | SR | 165 | 165 | 132 | Wind | 132 | 18-04-26 (66MW) | 66 |  | 66 |  |  |  | 66 |  | 66
[5 empty] | 135.3 | 135.3 | 120.725 | Solar | 0 | [5 empty] | 20-04-26 | 120.725 |  |  | 120.725
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total installed capacity of plant was 300 MW but 59.7 MW extra inverters installed for reactive power compensation
Note on F38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Installed capacity of this plant was 270 MW JSW done studies for 70 WTG's only i.e., 70 * 2.7 = 189
Note on F39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total installed capacity of plant was 300 MW but 52 MW extra inverters installed for reactive power compensation
Note on H87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: During march month applied, ToC issued for the 40.95 MW quantum on 16.03.2025

## old source wise _21032026
SL NO | Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | RANK
|  | NR | SOLAR |  | 3660 | 2207.22 | 0 | 1441 | 184536 | 679 | 184601 | 679 | 138100 | 0 | 0 | 340.69 | 89.69 | 2346 |  |  | 1
1 | IB VOGT SOLAR SEVEN PRIVATE LIMITED(IBVSSPL) | Fatehgarh-III | Solar | NR | 300 | 300 | SOLAR | 300 | 13.03.2026 18.03.2026 |  | NA |  | ` | NA | 0 |  |  | 300 |  |  | 1
2 | RENEW SAMIR SHAKTI THREE PRIVATE LIMITED | Fatehgarh-III | Solar | NR | 300 | 300 | SOLAR | 300 |  | 210.31 | 16.03.2026 | 210.31 | 17.03.2026 |  |  | 89.69 | 89.69 | 300 |  |  | 1
3 | RENEW SOLAR SHAKTI THREE PRIVATE LIMITED(RSS3PL) | Fatehgarh-III | Solar | NR | 300 | 300 | SOLAR | 300 | 46328 | 300 | 46329 | 300 | 46094 | NA | [6 empty] | 1
4 | ADANI SOLAR ENERGY BARMER ONE LIMITED(ASEB1L)) | Fatehgarh-III | Solar | NR | 600 | 251 | SOLAR | 251 | 46096 |  | NA |  |  |  |  | 251 |  | 251 |  |  | 1
5 | Khaba Renewable Energy Private Limited (KREPL) | Fatehgarh-III | Solar | NR | 250 | 221 | SOLAR | 221 | 46056 | 100 | 46094 | 100 | 46095 | NA |  |  |  | 150 |  |  | 1
7 | PROJECT ELEVEN RENEWABLE POWER PRIVATE LIMITED(P11RPPL) | Bhadla-II | Solar | NR | 150 | 100 | SOLAR |  | NA |  | NA | [6 empty] | 150 |  |  | 1
8 | PROJECT SIXTEEN RENEWABLE POWER PRIVATE LIMITED(P16RPPL) | Bhadla-II | Solar | NR | 300 | 200 | SOLAR |  | NA |  | NA |  |  | Annexure-B Yet to Submitted |  |  |  | 300 |  |  | 1
12 | Clean Max Celestial Private Limited(CMCPL) | Bikaner-II | Solar | NR | 250 | 234.57 | SOLAR |  | NA |  | NA |  |  | B ANX RETURNED |  |  |  | 234.57 |  |  | 1
13 | Clean Max Enviro Energy Solutions Limited(CMEESL) | Bikaner-II | Solar | NR | 100 | 93.75 | SOLAR |  | NA |  | NA |  |  | B ANX RETURNED |  |  |  | 93.75 |  |  | 1
14 | Energizent POWER Private Limited | Fatehgarh-III | Solar | NR | 250 | 60.6 | SOLAR | 69 |  | 69 | 45849 | 69 | 45911 |  |  |  |  | 69 |  |  | 1
15 | BBMB Panipat | Panipat | Solar | NR | 10 | 8.8 | SOLAR |  | 46056 |  | 46329 | [6 empty] | 10 |  |  | 1
17 | Adani Green Energy Twenty Five B Limited (AGE25BL) | Ramgarh-II | Solar | NR | 500 | 137.5 | SOLAR | NA | [9 empty] | 137.5 |  |  | 1
18 | Teq Green POWER XVIII Private Limited | Fatehgarh-III | Solar | NR | 50 | FTC yet to apply | [11 empty] | 50 |  | 50 | 1
19 | HRP Green POWER Private Limited | Bhadla-III | Solar | NR | 300 | FTC yet to apply | [11 empty] | 300 |  | 300 | 1
|  | NR | BESS |  | 835 | 342.432 | 0 | 342 | 46097 | 143 | 0 | 67 | 0 | 0 | 0 | 95 | 0 | 342 |  |  | 2
9 | ACME SUN POWER PRIVATE LIMITED(ASPPL) | Bhadla-II | BESS | NR | 300 | 100.003 | BESS | 100.003 | 66.67 FTC completed on 26-02-2026. 33.33 MW 17 MAR 26 | 66.67 | 33.335 MW 06-03-2026 33.335 MW 12-03-2026 | 66.67 | 33.335 MW Commercial Operation Date on 08-03-2026 33.335 MW Commercial Operation Date on 14-03-2026 |  |  |  |  | 100.003 |  |  | 2
10 | ACME SURYODAYA PRIVATE LIMITED(ACME_SPL) | Fatehgarh-I | BESS | NR | 285 | 171 | BESS | 171 | 76 MW FTC completed on 10-02-2026. 95 MW FTC APPROVED 14 MAR 2026 | 76 | 19 MW 25-02-2026 38 MW 03-03-2026 19 MW11-03-2026 |  | 19 MW 27-02-2026 38 MW 05-03-2026 19 MW13-03-2026 | 15-03-2026 |  | 95 |  | 171 |  |  | 2
11 | ACME Surya POWER Private Limited (ASRPPL) | Bikaner-II | BESS | NR | 250 | 71.429 | BESS | 71.429 | 46097 |  | NA | [6 empty] | 71.429 |  |  | 2
|  | NR | HYBRID |  | 715 | 275 | SOLAR+BESS | 465 | Solar:16.03.2026 BESS: 17.03.2026 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 178 |  |  | 3
6 | Juniper Green Stellar Private Limited(JGSPL) | Fatehgarh-IV | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) | NR | 715 | 275 | SOLAR+BESS | 465 | Solar:16.03.2026 BESS: 17.03.2026 |  | NA |  |  |  | 0 |  |  | 178 |  | Capacity(MW) applied for FTC_ Solar- 185 BESS-180 | 3
|  | NR | PUMPED STORAGE |  | 1000 | 250 | PSP HYDRO | 1000 | 46176 | 750 | 0 | 750 | 0 | 0 | 0 | 250 | 250 | 0 |  |  | 4
16 | Tehri | - | Pump Storage | NR | 1000 | 250 | PSP HYDRO | 1000 | 46176 | 750 |  | 750 |  |  |  | 250 | 250 | 0 |  |  | 4
SL NO | Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | RANK
|  | WR | WIND |  | 2621 | 0 | 0 | 611 | 0 | 507 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 700 |  |  | 1
1 | AGE26AL Khavda PSS6 | KPS1 | Solar | WR | 750 | 100 | Solar | 458 | 46101 | 350 | 2026-03-17 | 358 | 2026-03-20 |  | 100 | 100 | 100 | 258 |  |  | 4
2 | ASEJ6PL Khavda PSS8 | KPS3 | Wind | WR | 62.4 | 0 | Wind | 62.4 | 46087 | 52 | 2026-03-17 | 52 | 2026-03-20 |  | 0 | 10.4 | 10.4 | 62.4 |  |  | 2
3 | AGE24L SRPL Khavda PSS10 | KPS3 | Solar | WR | 150 | 0 | Solar | 150 | 46094 | 50 | 2026-01-21 | 50 | 2026-01-23 |  | 0 | 100 | 100 | 100 |  |  | 4
4 | AGE24L Khavda PSS5 | KPS1 | Solar | WR | 150 | 0 | Solar | 150 | 46069 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 75 |  |  | 4
5 | AGE26BL Khavda PSS10 | KPS3 | Solar | WR | 150 | 0 | Solar | 150 | 46069 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 100 |  |  | 4
6 | AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) | WR | 298 | 0 | Hybrid | 298 | 46090 | 298 | 2026-03-17 | 298 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  |  | 8
7 | ARE43L BESS - SRPL Khavda PSS10 | KPS3 | BESS | WR | 475 | 0 | BESS | 400 | 46097 | 160 | 2026-03-17 | 160 | 2026-03-20 |  | 0 | 0 | 0 | 395 |  |  | 6
8 | AGE26AL - SRPL Khavda PSS12 | KPS3 | Wind | WR | 140.4 | 0 | Wind | 140.4 | 46093 | 140.4 | 2026-03-20 | 137.5 | 2026-03-22 |  | 0 | 0 | 0 | 137.5 |  |  | 2
9 | ARE37L BESS - AGEL Khavda PSS5 | KPS1 | BESS | WR | 475 | 80 | BESS | 160 | 46101 | [5 empty] | 160 |  |  | 475 |  |  | 6
10 | Renew Green MHS One Pvt Ltd - RGESPL PSS-1 | Solapur | Wind | WR | 181.5 | 0 | Wind | 161.7 | 46087 | 155.1 | 2026-02-23 | 155.1 | 2026-02-25 |  |  | 6.6 | 26.4 | 6.6 |  |  | 2
11 | Avaada GJ Sustainable Private Limited | Lakadiya | Solar | WR | 200 | 91 | Solar | 109 | 46021 | 109 | 2026-02-04 | 109 | 2026-02-07 |  | 91 |  | 91 | 91 |  |  | 4
|  | WR | SOLAR |  | 5220 | 0 | Wind | 3409 | 46076 | 3096 | 0 | 2939 | 0 | 0 | 0 | 81.9 | 81.9 | 1922 |  |  | 3
15 | Sprng Akshay Urja Pvt Ltd | Rajgarh | Wind | WR | 167.2 | 0 | Wind | 165 | 46035 | 159.4 | 46069 | 159.4 | 46071 |  |  | 3.3 | 3.3 | 3.3 |  |  | 2
12 | Veh Saurya Urja Pvt Ltd | Pachora | Wind | WR | 163.2 | 0 | Wind | 81.9 | 46076 | 0 |  | 0 |  |  |  | 81.9 | 81.9 | 81.9 |  |  | 2
13 | Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) | WR | 181 | 0 | Solar | 52.8 | 46078 | 0 |  | 0 |  |  | 0 | 52.8 | 52.8 | 52.8 |  |  | 8
14 | Juniper Green Energy Limited | Jam Khambhaliya | Wind | WR | 300 | 0 | Wind | 0 | [9 empty] | 100 | Wind FTC application yet to be submitted | PSS FTC - protection coordination pendding from site, hence protection consent is remaining | 2
16 | TEQ Green POWER XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) | WR | 204.1 | 40.775 | Solar | 157.525 | 46015 | 144.025 | 46031 | 144.025 | 46033 |  | 40.775 | 13.5 | 13.5 | 27.275 |  |  | 8
17 | NTPC REL Khavda PSS2 | KPS2 | Solar | WR | 1555 | 78 | Solar | 1477 | 46027 | 1477 | 46059 | 1477 | 46064 |  |  |  | 78 | 78 |  |  | 4
18 | NTPC REL Khavda PSS1 | KPS3 | Solar | WR | 1200 | 285 | Solar | 915 | 46027 | 810 | 46099 | 645 | 46093 |  | 85 | 270 | 555 | 555 | CONN-TD-4 remaining for 200 MW |  | 4
19 | NTPC REL Vanki | Bhuj | Wind | WR | 165 | 116.55 | Wind | 0 | [9 empty] | 56.7 | CAT-2 yet to be received | Combined with lead generator Ayana | 2
20 | Coal India Limited at GIPCL | KPS2 | Solar | WR | 300 | 300 | Solar | 0 | [9 empty] | 100 | CAT-2 yet to be received | POWER park developer GIPCL | 4
21 | NTPC REL at GSECL | KPS2 | Solar | WR | 265 | 64.76 | Solar | [7 empty] | 64.76 |  |  | 65 | CAT-2 yet to be received | POWER park developer GSECL | 4
|  | WR | BESS |  | 1266 | 0 | Solar | 560 | 0 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 950 |  |  | 5
23 | JSW Renew Energy Ten Ltd at GSECL | KPS2 | Solar | WR | 300 | 0 | Solar | [10 empty] | 300 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS | 4
22 | Engie Energy India Pvt Ltd at GSECL | KPS2 | Solar | WR | 200 | 0 | Solar | [10 empty] | 200 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS | 4
24 | Mounting Renewable POWER Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) | WR | 250 | 128.7 | Hybrid | [7 empty] | 128.7 | 0 | 0 | 99 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar | 8
|  | WR | HYBRID |  | 1162 | 0 | Wind | 508 | 0 | 442 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 179 |  |  | 7
28 | ARE36L BESS - AGEL Khavda PSS8 | KPS3 | BESS | WR | 316 | 0 | BESS | [10 empty] | 80 | CAT-2 yet to be received | FTC application yet to be submitted for BESS | 6
25 | Serentica Renewables India4 Pvt Ltd | Kallam | Wind | WR | 350 | 0 | Wind | [10 empty] | 66 | CAT-2 yet to be received | FTC application yet to be submitted for Wind | 2
26 | AirPOWER Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind+BESS) | WR | 229 | 0 | Hybrid | [10 empty] | 0 | CAT-2 yet to be received | FTC application yet to be submitted for Wind, Solar | 8
27 | Oyster Green Hybrid One Pvt Ltd at Dayapar | Bhuj | Wind | WR | 99 | 0 | Wind | [10 empty] | 50 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind | 2
29 | AGE25CL Khavda PSS14 | KPS3 | Wind | WR | 67.6 | 67.6 | Wind | [10 empty] | 62.4 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind | 2
30 | AGE26AL Khavda PSS14 | KPS3 | Wind | WR | 295 | 0 | Wind | [10 empty] | 72.8 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind | 2
31 | NTPC REL at Jamjodhpur | Jam Khambhaliya | Wind | WR | 630 | 0 | Wind | [11 empty] | CAT-2 yet to be received | FTC application yet to be submitted for Wind | 2
SL NO | Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | RANK
|  |  | SR WIND |  | 489 |  |  | 298 |  | 217 |  | 217 | [5 empty] | 15 |  |  | 1
1 | Serentica Renewables India 1 Private Limited | Koppal | Hybrid(wind+Solar) | SR | 399.8 | 40.95 | Wind | 386.7 | 11-02-2026, 12-03-2026 | 386.7 | 10-03-2026, 16-03-2026 | 386.7 | 10-03-2026, 18-03-2026 | [6 empty] | No pending Requests | 6
2 | Serentica Renewables India 3 Private Limited | Gadag | Hybrid(wind+Solar) | SR | 470 | 62.095 | Wind / Solar | 354.8 | 26-02-2026 , 10-03-2026, 18-03-2026 | 306.565 | 46359 | 306.565 | 46359 |  |  | 48.235 |  | 48.235 |  | 34.375 MW Solar Trial Run on 17.03.2026 . 13.86MW Wind FTC cleared on 18.03.2026 | 6
|  |  | SR SOLAR |  | 360 |  |  | 360 |  | 360 |  | 300 | [5 empty] | 0 |  |  | 3
3 | SAEL Solar MHP2 Pvt Ltd | Kurnool-III | Solar | SR | 359.7 | 92.4 | Solar | 359.7 | 26-02-2026 | 359.7 | 13-03-2026 | 300 | 13-03-2026 | [6 empty] | Total plant commissioned | 4
|  |  | SR HYBRID |  | 4050 |  |  | 2671 |  | 2623 |  | 2218 | [5 empty] | 48 |  |  | 5
5 | Sembcorp Green Infra Pvt. Ltd. | Gadag | Wind | SR | 300 | 54.6 | Wind | 109.2 | 01-09-2025 , 13-02-2026 , 11-02-2026 | 54.6 |  | 54.6 |  |  |  | 54.6 |  | 14.7 |  | Clarification on FFR to be submitted by Developer . Developer doing Retrial run for 11 WTGs on 17.03.2026 | 2
4 | Greenko AP01 IREP Pvt Ltd | Kurnool | Hybrid with PSP_Solar | SR | 3180 | 264 | Solar | 1929.425 | 46296 | 1929.425 | 14-03-2026 | 1524.25 | 18-03-2026 |  |  |  | 405.175 |  |  | Developer informed that 249.425 MW out of 264 MW connected and TOC/COD for same is done. COD not yet declared for PSP U5 & U6 | 6
6 | JSW Renew Energy Limited | Karur | Wind | SR | 189 | 27 | Wind | 189 | 17-09-2025 | 162 |  | 162 |  |  |  | 27 |  |  |  | Plant PPC Report to be submitted by Developer. Slall approach commission for infirm injection approval. | 2
SL NO | Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | RANK
|  |  | ER COAL |  | 5980 |  |  | 4520 |  | 3060 |  | 3060
1 | PVUNL Unit-2 | - | Coal | ER | 2400 | 800 | Coal | 1600 | - | 800 | - | 800 | - | - | 0 | 800 | 800 | 0 | Generation at PVUNL is limited to 1200 MW (800+400) until SPS is implemented, owing to transmission constraints. | Format-IV has been issued on 16.03.2026. Infirm generation commenced on 17.03.2026 at 10:31 hrs, currently out since 20-03-2026 13:37 Hrs at generator protection.
2 | Sagardighi Unit-5 | - | Coal | ER | 2260 | 0 | Coal | 2260 | - | 2260 | - | 2260 | - | - |  |  |  | 0 |  | COD declared w.e.f. 00:00 hrs of 20.03.2026.
3 | Buxar Unit-2 | - | Coal | ER | 1320 | - | Coal | 660 | - | - | - | - | - | 46137 | - | - |  | 0 | - | It is an intrastate generating station connected to the Bihar system. As per the telephonic conversation, Unit-2 is likely to be synchronized with the grid in the last week of April 2026.
SL NO | Generating Station | Pooling Station | Plant Type (Wind/Solar/BESS/Hybrid(wind+Solar)/Hybrid(Solar+BESS)/Hybrid(Wind+Solar+BESS).../Coal/Hydro etc) | Region | Total Plant Capacity(MW) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity (MW) | TOC issuance date if Completed | COD declared Capacity (MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | RANK
|  |  | NER SOLAR |  | 70 |  |  | 70 |  | 70 |  | 70 | [5 empty] | 0 |  |  | 1
6 | SJVN Solar | - | Solar |  | 70 |  | Solar | 70 | 31-01-2026 | 70 | 46083 | 70 | 06.03.2026 | NA | [5 empty] | TOC issused by SLDC Assam on 06.03.2026 | 1
|  |  | NER HYDRO |  | 2120 |  |  | 750 |  | 750 |  | 750 | [5 empty] | 0 |  |  | 2
1 | Subansiri Lower HEP | - | Hydro unit-1 | NER | 2000 | 250 | Hydro | 250 | 31-01-2026 | 250 | 46268 | 250 | 20-03-2026 | NA |  |  |  | 0 |  |  | 2
2 | Subansiri Lower HEP |  | Hydro_unit-4 | NER |  | 250 |  | 250 |  | 250 |  | 250 |  | 31-05-2026 |  |  |  | 0 |  | Under commissioning | 2
3 | Subansiri Lower HEP |  | Hydro_unit-5 | NER |  | 250 |  | 250 |  | 250 |  | 250 |  | 31-08-2026 |  |  |  | 0 |  | Under commissioning | 2
4 | Lower Kopili HEP | - | Hydro_unit-1 | NER | 120 | Yet to be applied | Hydro | 60 |  | 60 |  | 60 |  | 15-05-2026 |  |  |  | 0 |  | Under commissioning. Lower Kopili HEP (Intra-State) 120 MW (FTC application yet to be submitted) | 2
5 | Lower Kopili HEP | - | Hydro_unit-2 | NER |  |  |  | 60 |  | 60 |  | 60 |  | 15-05-2026 |  |  |  | 0 |  |  | 2

## Region wise
NR Generation Capacity Under Process of FTC
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity (MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | [5 empty] | Test
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total NR Wind |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | 1 | IB VOGT SOLAR SEVEN PRIVATE LIMITED(IBVSSPL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.03.2026 18.03.2026 | 200 | 27.03.2026 | 200 | 150MW (30.03.2026) 50MW (01.04.2026) |  | 0 | 0 | 0 | 100 | [5 empty] | 0 | 0 | 0
2 | 2 | RENEW SAMIR SHAKTI THREE PRIVATE LIMITED | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.02.2026 16.02.2026 | 300 | 210.31MW dated17.03.2026 64.67MW dated 24.03.2026 25.02 MW 31.03.2026 | 300 | 210.31MW dated 17.03.2026 64.67MW dated 26.03.2026 |  | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0
3 | 3 | RENEW SOLAR SHAKTI THREE PRIVATE LIMITED(RSS3PL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 46328 | 300 | 46329 | 300 | 46094 |  | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0
4 | 4 | ADANI SOLAR ENERGY BARMER ONE LIMITED(ASEB1L)) | Fatehgarh-III | Solar | NR | 600 | 600 | 251 | SOLAR | 251 | 46096 | 251 | 23-03-2026 | 251 | 25.03.2025 |  | 0 | 0 | 0 | 0 | [5 empty] | 349 | 0 | 0
5 | 5 | Khaba Renewable Energy Private Limited (KREPL) | Fatehgarh-III | Solar | NR | 250 | 250 | 221 | SOLAR | 221 | 46056 | 150 | 100MW on 13-03-26 50 MW on 27-03-2026 | 150 | 100MW-14 Mar 26 50MW-27 Mar 26 |  | 0 | 0 | 0 | 71 | [5 empty] | 29 | 0 | 0
6 | 7 | PROJECT ELEVEN RENEWABLE POWER PRIVATE LIMITED(P11RPPL) | Bhadla-II | Solar | NR | 150 | 150 | 100 | SOLAR | 100 | 25-03-2026 | 87.5 | 17.04.2025 | 87.5 | 21.04.2026 |  | 0 |  | 0 | 62.5 | [5 empty] | 0 | 0 | 0
7 | 8 | PROJECT 16 RENEWABLE POWER PRIVATE LIMITED(P16RPPL) | Bhadla-II | Solar | NR | 300 | 300 | 200 | SOLAR | 200 | 25-03-2026 | 150 | 16.04.2026 | 150 | 18.04.2026 |  | 0 |  | 0 | 50 | [5 empty] | 100 | 0 | 0
8 | 12 | Clean Max Celestial Private Limited(CMCPL) | Bikaner-II | Solar | NR | 250 | 250 | 234.57 | SOLAR | 0 | NA | [5 empty] | 234.57 |  | 0 | 250 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 234.57 | 0
9 | 13 | Clean Max Enviro Energy Solutions Limited(CMEESL) | Bikaner-II | Solar | NR | 100 | 100 | 93.75 | SOLAR | 0 | NA | [5 empty] | 93.75 |  | 0 | 100 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 93.75 | 0
10 | 14 | Energizent POWER Private Limited | Fatehgarh-III | Solar | NR | 250 | 250 | 129.6 | SOLAR | 129.6 | 60.6 MW on 27-03-2026 69 MW on 29-10-2025 | 69 | 45849 | 69 | 45911 |  | 0 |  | 0 | 60.6 | [5 empty] | 120.4 | 0 | 0
11 | 15 | BBMB Panipat | Panipat | Solar | NR | 10 | 8.8 | 8.8 | SOLAR | 8.8 | 46056 | 8.8 | 46329 | 8.8 | 46329 |  | 0 |  | 0 | 0 | [5 empty] | 1.2 | 0 | 0
12 | 17 | Adani Green Energy Twenty Five B Limited (AGE25BL) | Ramgarh-II | Solar | NR | 500 | 500 | 137.5 | SOLAR | 137.5 | 23-03-2026 | 137.5 | 28-03-2026 | 137.5 | 30-03-2026 |  | 0 |  | 0 | 362.5 | [5 empty] | 0 | 0 | 0
13 | 18 | Teq Green POWER XVIII Private Limited | Fatehgarh-III | Solar | NR | 50 | 50 | 0 | SOLAR | 0 | [6 empty] | 0 |  | 0 | 50 |  | FTC yet to apply for FTC |  |  |  | 0 | 0 | 0
14 | 19 | Renew Solar Shakti Five Private Limited | Fatehgarh-III | Solar | NR | 400 | 400 | 400 | SOLAR | 400 | 200MW on 25-03-2026 200MW on 28-03-2026 | [5 empty] | 0 |  | 0 | 400 |  | Annexure B returb 24.03.26 |  |  |  | 0 | 0 | 0
15 | 21 | HRP Green POWER Private Limited | Bhadla-III | Solar | NR | 300 | 296 | 0 | SOLAR | 296 | 2026-01-04 | 148 | 13.04.2026 | 148 | 148MW 13.04.2026 |  | 0 |  | 0 | 148 | [5 empty] | 4 | -296 | 0
16 | [27 empty] | 1
17 | [27 empty] | 1
18 | [27 empty] | 1
19 | [27 empty] | 1
20 | [27 empty] | 1
| Total NR Solar |  |  |  |  | 4060 |  | 2676.22 | 0 | 2643.9 | 230562 | 1801.8 | 138507 | 1801.8 | 138334 | 0 | 328.32 | 0 | 0 | 1654.6 | [7 empty] | 0
1 | 9 | ACME SUN POWER PRIVATE LIMITED(ASPPL) | Bhadla-II | BESS | NR | 300 | 300 | 166.665 | BESS | 166.665 | 66.66 FTC completed on 26-02-2026. 33.33 MW 17 MAR 26 66.66MW 24-03-2026 33.33MW | 166.665 | 33.335 MW 06-03-2026 33.335 MW 12-03-2026 33.33MW- 31.03.2026 33.33MW- 01.04.2026 33.334MW-06.04.2026 | 166.665 | 33.335 MW on 08-03-2026 33.335 MW on 14-03-2026 33.333 MW on 02-04-2026 33.333 MW on 03-04-2026 33.334 MWon 08-04-2026 |  | 0 |  | 0 | 133 | [5 empty] | 0.335 | 0 | 0
2 | 10 | ACME SURYODAYA PRIVATE LIMITED(ACME_SPL) | Fatehgarh-I | BESS | NR | 300 | 285 | 285 | BESS | 285 | 76 MW FTC completed on 10-02-2026. 95 MW FTC APPROVED 14 MAR 2026 114 MW FTC issued on 29-03-2026 | 285 | 19 MW 25-02-2026 38 MW 03-03-2026 19 MW11-03-2026 95MW-23.03.2026 76MW-06.04.2026 | 285 | 19 MW on 27-02-2026 38 MW on 05-03-2026 19 MW on 13-03-2026 95 MW on 25-03-2026 76 MW on 08-04-2026 38MW on 13-04-2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 15 | 0 | 0
3 | 11 | ACME Surya POWER Private Limited (ASRPPL) | Bikaner-II | BESS | NR | 250 | 250 | 142.857 | BESS | 142.857 | 16-03-2026 (71.43MW) 17-03-2026 (35.71MW) 24-03-2026 (35.71MW) | 139.509 | 23-03-2026 (60MW) 24-03-2026 (35.71MW) 29-03-2026 (11.429MW) | 139.509 | 60MW dated 23.03.26 35.714 dated 24-03-26 11.429 MW on 29-03-26 32.366MW on 13-04-26 |  | 0 | 0 | 0 | 110.491 | [5 empty] | 1.4211e-14 | 0 | 0
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
| Total NR BESS |  |  |  |  | 850 |  | 594.522 | 0 | 594.522 | 0 | 591.174 | 0 | 591.174 | 0 | 0 | 0 | 0 | 0 | 243.491 | [7 empty] | 0
1 | 6 | Juniper Green Stellar Private Limited(JGSPL) | Fatehgarh-IV | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) | NR | 715 | 365 | 365 | SOLAR+BESS | 465 | Solar:16.03.2026 (185MW) 06.04.2026 (100MW) BESS: 17.03.2026 (90MW) 21.03.2026 (90 MW) | 365 | 88MW solar-25.03.26 90MW-BESS 02-04-2026 10.04.2026 (97 MW Solar) 90MW BESS 22.04.2026 | 365 | 27 Mar 26-88MW solar 12.04.26 97MW Solar 90MW BESS-08.04.2026 90MW BESS 24.04.2026 |  | 0 | 0 | 0 | 187 |  | Capacity(MW) applied for FTC_ Solar- 185 BESS-180 | TOC Isuued capcity: 88-solar 90MW-BESS | COD Declared capcity: 88-solar 90MW-BESS | Capacity(MW) commisioning expected in Apr'26: (187)solar-97 Bess-90 | 163 | -100 | 0
2 | 20 | AMPIN ENERGY GREEN TEN PRIVATE LIMITED(AEG10PL) | Fatehgarh-IV | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) | NR | 155 | 120 | 155 | solar+Wind | 155 | 2026-12-02 | 155 | 27.03.2026 | 155 | 114.4MW--04.04.2026 40.4MW- 04.04.2026 |  | 0 |  |  |  |  | TOC Isuued capcity: 120(solar-114.4+wind-40.4) |  |  |  | 0 | 0 | 0
3 | 22 | Aditya Birla Renewables subsdiary Ltd | Fatehgarh-III | Hybrid_(292MVA Solar, 287MVA Wind) | NR | 608 not applied | 608 not applied | 0 | Solar+Wind | 0 | [6 empty] | 0 |  | 0 | 608 not applied | Hybrid_(292MVA Solar, 287MVA Wind) | Registration and Conn6 pending |  |  |  | #VALUE! | 0 | 0
4 | [27 empty] | 1
| Total NR Hybrid |  |  |  |  | 870 |  | 520 | 0 | 620 | 46358 | 520 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 187 | [7 empty] | 0
1 | 23 | Ghatampur TPS | Ghatampur | Thermal | NR | 660 | 660 | 660 | Thermal | 660 | 30-03-2026 | [5 empty] | 660 |  |  | 660 | [5 empty] | 0 |  | 0
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
5 | [27 empty] | 1
| Total NR Coal |  |  |  |  | 660 |  | 660 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 660 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total NR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | 16 | Tehri | - | Pump Storage | NR | 1000 | 1000 | 1000 | PSP HYDRO | 1000 | 46176 | 1000 | 250 MW U#4 on 10.04.2026 | 1000 | 12.04.2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
| Total NR PSP |  |  |  |  | 1000 |  | 1000 | 0 | 1000 | 46176 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| Total NR |  |  |  |  | 7440 |  | 5450.742 | 0 | 5518.422 | 323096 | 3912.974 | 138507 | 3912.974 | 138334 | 0 | 988.32 | 0 | 0 | 2745.091 | [7 empty] | 0
0
WR Generation Capacity Under Process of FTC | [27 empty] | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | [5 empty] | 0
1 | 2 | ASEJ6PL Khavda PSS8 | KPS3 | Wind | WR | 62.4 | 62.4 | 62.4 | Wind | 62.4 | 46087 | 62.4 | 46109 | 62.4 | 46109 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
2 | 9 | AGE26AL - SRPL Khavda PSS12 | KPS3 | Wind | WR | 140.4 | 137.5 | 140.4 | Wind | 140.4 | 46093 | 140.4 | 46101 | 137.5 | 46103 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.9 |  | 0 | 2.9 |  | 0
3 | 11 | Renew Green MHS One Pvt Ltd - RGESPL PSS-1 | Solapur | Wind | WR | 181.5 | 181.5 | 181.5 | Wind | 161.7 | 46087 | 161.7 | 46107 | 161.7 | 46108 |  | 19.8 | 0 | 0 | 19.8 |  |  | 0 |  | 19.8 | 0 |  | 0
4 | 13 | Veh Saurya Urja Pvt Ltd | Pachora | Wind | WR | 163.2 | 81.9 | 81.9 | Wind | 81.9 | 46076 | 69.3 | 46106 | 69.3 | 46107 |  | 0 | 0 | 0 | 0 |  |  | -93.9 |  | 0 | 0 |  | 0
5 | 15 | Juniper Green Energy Limited | Jam Khambhaliya | Wind | WR | 300 | 100 | 0 | Wind | 0 | [6 empty] | 0 |  | 0 | 100 | Wind FTC application yet to be submitted | PSS FTC - protection coordination pending from site, hence protection consent is remaining | -200 |  | 0 | 0 |  | 0
6 | 16 | Sprng Akshay Urja Pvt Ltd | Rajgarh | Wind | WR | 167.2 | 165 | 165 | Wind | 165 | 46035 | 165 | 46120 | 162.7 | 100: 29-12-2025 16.5: 31-12-2025 6.6: 05-01-2026 6.6: 28-01-2026 13.2: 30-01-2026 6.6: 04-02-2026 9.9: 18-02-2026 3.3: 10-04-2026 |  | 0 | 0 | 2.3 | 3.3 |  |  | -1.2 |  | 0 | 2.3 |  | 0
7 | 22 | NTPC REL Vanki | Bhuj | Wind | WR | 165 | 0 | 116.55 | Wind | 50.4 | 46132 | [5 empty] | 66.15 |  | 0 | 50.4 |  | Combined with lead generator Ayana | -114.6 |  | 66.15 | 0 |  | 0
8 | 28 | Serentica Renewables India4 Pvt Ltd | Kallam | Wind | WR | 350 | 250 | 66 | Wind | 66 | 46112 | [5 empty] | 0 | 66 | 0 | 66 |  |  | -284 |  | 0 | 0 |  | 0
9 | 30 | Oyster Green Hybrid One Pvt Ltd at Dayapar | Bhuj | Wind | WR | 99 | 99 | 0 | Wind | [7 empty] | 0 |  | 0 | 0 |  | FTC application yet to be submitted for Wind - proposed in April | -99 |  | 0 | 0 |  | 0
10 | 32 | AGE25CL Khavda PSS14 | KPS3 | Wind | WR | 67.6 | 65 | 67.6 | Wind | 67.6 | 46106 | 67.6 | 46109 | 65 | 46109 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.6 |  | 0 | 2.6 |  | 0
11 | 33 | AGE26AL Khavda PSS14 | KPS3 | Wind | WR | 208 | 208 | 130 | Wind | 130 | 46125 | 67.6 | 46134 | 67.6 | 46134 |  | 0 |  | 0 | 130 |  |  | -10.4 |  | 0 | 0 |  | 0
12 | 34 | NTPC REL at Jamjodhpur | Jam Khambhaliya | Wind | WR | 630 | 0 | 53.55 | Wind | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received |  | -630 |  | 53.55 | 0 |  | 0
13 | 36 | Continuum Power Trading (TN) Private Limited | Bhuj | Wind | WR | 36 | 36 | 0 | Wind | [7 empty] | 0 |  | 0 | 36 |  | FTC application yet to be submitted for Wind - proposed in April | 0 |  | 0 | 0 |  | 0
14 | 39 | Sprng Vayu Vidyut Pvt Ltd | Rajgarh | Wind | WR | 198 | 0 | 0 | Wind | [10 empty] | 105 | CAT-2 yet to be received | [6 empty] | 0
15 | [27 empty] | 1
16 | [27 empty] | 1
17 | [27 empty] | 1
| Total WR Wind |  |  |  |  | 2768.3 |  | 1064.9 | 0 | 925.4 | 414853 | 734 | 322786 | 726.2 | 276670 | 0 | 85.95 | 66 | 2.3 | 510.5 | [7 empty] | 0
1 | 1 | AGE26AL Khavda PSS6 | KPS1 | Solar | WR | 750 | 750 | 750 | Solar | 750 | 46126 | 750 | 46132 | 750 | 50: 25-01-2026 250: 15-03-2026 50: 21-03-2026 50: 29-03-2026 50: 16-04-2026 58: 01-04-2026 242: 20-04-2026 |  | 0 | 0 | 0 | 0 | CEA EI approval yet to be received | Full COD complete | 0 |  | 0 | 0 |  | 0
2 | 3 | AGE25CL Khavda PSS8 | KPS3 | Solar | WR | 500 | 500 | 500 | Solar | 500 | 46108 | 375 | 46111 | 350 | 46111 |  | 0 | 125 | 25 | 150 |  |  | 0 |  | 0 | 25 |  | 0
3 | 4 | AGE24L SRPL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 46094 | 100 | 46106 | 100 | 46107 |  | 0 | 50 | 0 | 50 |  |  | 0 |  | 0 | 0 |  | 0
4 | 5 | AGE24L Khavda PSS5 | KPS1 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 46069 | 150 | 46098 | 150 | 46101 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
5 | 6 | AGE26BL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 46069 | 150 | 46098 | 150 | 46101 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
6 | 12 | Avaada GJ Sustainable Private Limited | Lakadiya | Solar | WR | 200 | 200 | 200 | Solar | 200 | 46105 | 200 | 46119 | 200 | 108.33: 07-02-2026 91.67: 11-04-2026 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
7 | 19 | Ayana Power Four Private Limited at Zura | Bhuj | Solar | WR | 150 | 150 | 150 | Solar | 150 | 46098 | 150 | 46112 | 150 | 46112 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
8 | 20 | NTPC REL Khavda PSS2 | KPS2 | Solar | WR | 1555 | 1555 | 1555 | Solar | 1555 | 46104 | 1555 | 46111 | 1555 | 46111 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
9 | 21 | NTPC REL Khavda PSS1 | KPS3 | Solar | WR | 1200 | 1095 | 1200 | Solar | 1095 | 46123 | 1005 | 46111 | 1005 | 46111 |  | 105 | 90 | 0 | 195 | CONN-TD-4 remaining for 105 MW |  | 0 |  | 105 | 0 |  | 0
10 | 23 | Coal India Limited at GIPCL | KPS2 | Solar | WR | 300 | 0 | 300 | Solar | 0 | [6 empty] | 300 |  | 0 | 0 | CAT-2 yet to be received | POWER park developer GIPCL - proposed in April | -300 |  | 300 | 0 |  | 0
11 | 24 | NTPC REL at GSECL | KPS2 | Solar | WR | 265 | 0 | 64.76 | Solar | 64.76 | 46133 | [5 empty] | 0 |  | 0 | 64.76 |  | POWER park developer GSECL | -200.24 |  | 0 | 0 |  | 0
12 | 25 | Engie Energy India Pvt Ltd at GSECL | KPS2 | Solar | WR | 200 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 200 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS - proposed in April | 0 |  | 0 | 0 |  | 0
13 | 26 | JSW Renew Energy Ten Ltd at GSECL | KPS2 | Solar | WR | 300 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 300 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS already commuincated through mail for submission of FTC application but it is stiil not received as on 27.03.26 | 0 |  | 0 | 0 |  | 0
14 | 38 | Waree Energies Limited | Rewa | Solar | WR | 170 | 0 | 170 | Solar | [10 empty] | 170 | CAT-2 yet to be received | [6 empty] | 0
15 | [27 empty] | 1
16 | [27 empty] | 1
| Total WR Solar |  |  |  |  | 6040 |  | 5339.76 | 0 | 4764.76 | 461029 | 4435 | 414998 | 4410 | 322754 | 0 | 405 | 265 | 25 | 1129.76 | [7 empty] | 0
1 | 8 | ARE43L BESS - SRPL Khavda PSS10 | KPS3 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 46097 | 400 | 46127 | 400 | 80: 11-03-2026 80: 20-03-2026 60: 28-03-2026 120: 30-03-2026 20: 02-04-2026 20: 11-04-2026 20: 15-04-2026 |  | 80 | 0 | 0 | 75 |  |  | 0 |  | 80 | 0 |  | 0
2 | 10 | ARE37L BESS - AGEL Khavda PSS5 | KPS1 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 46122 | 320 | 46129 | 320 | 80: 01-04-2026 80: 01-04-2026 80: 11-04-2026 60: 15-04-2026 20: 17-04-2026 |  | 80 | 80 | 0 | 155 |  |  | 0 |  | 80 | 0 |  | 0
3 | 31 | ARE36L BESS - AGEL Khavda PSS8 | KPS3 | BESS | WR | 316 | 284 | 320 | BESS | 280 | 46136 | 80 | 46135 | 80 | 46136 |  | 40 | 200 | 0 | 160 |  |  | -76 |  | 40 | 0 |  | 0
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
7 | [27 empty] | 1
| Total WR BESS |  |  |  |  | 1266 |  | 1280 | 0 | 1080 | 138355 | 800 | 138391 | 800 | 46136 | 0 | 200 | 280 | 0 | 390 | [7 empty] | 0
1 | 7 | AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) | WR | 298 | 216 | 298 | Hybrid | 298 | 46090 | 298 | 46098 | 298 | 46101 |  | 0 | 0 | 0 | 0 |  | Hybrid connectivity 216 MW Full COD complete | 0 |  | 0 | 0 |  | 0
2 | 14 | Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) | WR | 181 | 67 | 52.8 | Solar | 52.8 | 46078 | 52.8 | 46106 | 52.8 | 46107 |  | 0 | 0 | 0 | 0 |  |  | -128.2 |  | 0 | 0 |  | 0
3 | 17 | TEQ Green Power XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) | WR | 204.1 | 150.3 | 201 | Hybrid | 174 | 46134 | 160.225 | 46113 | 160.225 | Wind: 18.9: 30-06-2025 32.4: 30-06-2025 13.5: 16-08-2025 13.5: 02-10-2025 2.7: 07-11-2025 5.4: 29-11-2025 10.8: 20-12-2025 16.2: 03-04-2026 Solar: 24.425: 16-08-2025 22.4: 11-01-2026 |  | 27 | 0 | 0 | 40.775 |  |  | -3.1 |  | 27 | 0 |  | 0
4 | 18 | Ayana Power Four Private Limited at Devasar | Bhuj | Hybrid (Solar + Wind) | WR | 129.9 | 100 | 129.9 | Hybrid | 129.9 | 45848 | 129.9 | 46112 | 129.9 | 46112 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 |  | 0
5 | 27 | Mounting Renewable Power Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) | WR | 250 | 0 | 128.7 | Hybrid | [7 empty] | 128.7 | 0 | 0 | 128.7 | CAT-2 yet to be received |  | -121.3 |  | 128.7 | 0 |  | 0
6 | 29 | Airpower Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind+BESS) | WR | 229 | 140 | 81.25 | Hybrid | [7 empty] | 0 |  | 0 | 50 |  |  | -179 |  | 81.25 | 0 |  | 0
7 | 35 | Veh Jayin Renewables Private Limited | Rajgarh | Hybrid (Solar + Wind) | WR | 196.8 | 0 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in April | -196.8 |  | 0 | 0 |  | 0
8 | 37 | Aditya Birla Renewable Energy Limited (ABREL) Valsara | Bhuj-II | Hybrid (Solar + Wind) | WR | 314 | 294 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CONN-TD-4 signed, CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in May | -314 |  | 0 | 0 |  | 0
9 | [27 empty] | 1
| Total WR Hybrid |  |  |  |  | 1802.8 |  | 891.65 | 0 | 654.7 | 184150 | 640.925 | 184429 | 640.925 | 138320 | 0 | 155.7 | 0 | 0 | 219.475 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total WR Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total WR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total WR PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
| Total WR |  |  |  |  | 11877.1 |  | 8576.31 | 0 | 7424.86 | 1198387 | 6609.925 | 1060604 | 6577.125 | 783880 | 0 | 846.65 | 611 | 27.3 | 2249.735 | [7 empty] | 0
0
SR Generation Capacity Under Process of FTC | [27 empty] | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity (MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | [5 empty] | 0
1 | 2 | Sembcorp Green Infra Pvt. Ltd. | Gadag | Wind | SR | 300 | 262 | 109.2 | Wind | 109.2 | 01-09-2025 , 13-02-2026 , 11-02-2026 | 69.3 |  | 69.3 | 17-01-2025 |  | 0 | 39.9 | 0 | 39.9 |  | ToC for 14.7 MW issued on 23.03.26 |  | 0 | 0 |  |  | 0
2 | 3 | JSW Renew Energy Limited | Karur | Wind | SR | 189 | 150 | 189 | Wind | 189 | 17-09-2025 | 162 |  | 162 | 09.05.25 (32.4MW) 28.03.25 (43.2 MW) 27.03.25 (27 MW) 28.02.25 (59.4 MW) |  | 0 |  | 0 |  |  | Remaining 10 WTG's of 2.7 MW Plant PPC Report to be submitted by Developer but period for infirm injection i.e., 45 days plus 3 months expired . M/s JSW has to approach commission for infirm injection approval. |  | 0 | 0 |  |  | 0
3 | [27 empty] | 1
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
| Total SR Wind |  |  |  |  | 489 |  | 298.2 | 0 | 298.2 | 0 | 231.3 | 0 | 231.3 | 0 | 0 | 0 | 39.9 | 0 | 39.9 | [7 empty] | 0
1 | 1 | SAEL Solar MHP2 Pvt Ltd | Kurnool-III | Solar | SR | 359.7 | 300 | 359.7 | Solar | 359.7 | 26-02-2026 | 359.7 | 13-03-2026 | 300 (359.7) | 09-01-2026 (156.88 MW) , 23-02-2026 ( 66.06 MW) , 13-03-2026 (77.06 MW) |  | 0 |  | 0 |  |  | Total plant commissioned |  | 0 | #VALUE! |  |  | 0
2 | 7 | TP Saurya Limited | Koppal | Solar | SR | 352 | 300 | 281.6 | Solar | 281.6 | 23-03-2026 | 281.6 | 52.8MW: 17.04.26 | 238.46 (281.6) | 08-01-2026 ( 130.77 MW), 03-02-2026 (61.54 MW), 18-04-2026 (46.15MW) |  | 0 | 0 | 0 | 52.8 |  |  |  | 0 | #VALUE! |  |  | 0
3 | 8 | NTPC Ramagundam (176MW) | Ramagundam | Solar | SR | 204.6 | 176 | 154.8 | Solar | 154.8 | 27-03-2026 |  |  |  | Trial run on 20.04.26 |  | 0 | 154.8 | 0 | 154.8 | [7 empty] | 0
4 | [27 empty] | 1
| Total SR Solar |  |  |  |  | 916.3 |  | 796.1 | 0 | 796.1 | 0 | 641.3 | 0 | 0 | 0 | 0 | 0 | 154.8 | 0 | 207.6 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total SR BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
7 | [27 empty] | 1
| Total SR Hybrid |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total SR Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total SR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total SR PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
| Total SR |  |  |  |  | 1405.3 |  | 1094.3 | 0 | 1094.3 | 0 | 872.6 | 0 | 231.3 | 0 | 0 | 0 | 194.7 | 0 | 247.5 | [7 empty] | 0
0
ER Generation Capacity Under Process of FTC | [27 empty] | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity (MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity (MW) | FTC date if completed | TOC Issued Capacity (MW) | TOC issuance date if Completed | COD declared Capacity (MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in Mar'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | [5 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total ER Wind |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total ER Solar |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total ER BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total ER Hybrid |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | 1 | PVUNL Unit-2 | - | Coal | ER | 2400 | 2400 | 2400 | Coal | 1600 | - | 800 | - | 800 | - | - | 800 | 800 | 0 | 800 | SPS has been implemented as per the undertaking submitted. | Format-IV has been issued on 16.03.2026. Trial operation of Unit #2 (800 MW) of Patratu STPP Phase-I (3×800 MW) is tentatively expected from 13.04.2026. |  |  |  | 800 |  | 0
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
7 | [27 empty] | 1
| Total ER Coal |  |  |  |  | 2400 |  | 2400 | 0 | 1600 | 0 | 800 | 0 | 800 | 0 | 0 | 800 | 800 | 0 | 800 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total ER Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total ER PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
| Total ER |  |  |  |  | 2400 |  | 2400 | 0 | 1600 | 0 | 800 | 0 | 800 | 0 | 0 | 800 | 800 | 0 | 800 | [7 empty] | 0
0
NER Generation Capacity Under Process of FTC | [27 empty] | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Plant Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity (MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Completed Capacity (MW) | FTC date if completed | TOC Issued Capacity (MW) | TOC issuance date if Completed | COD declared Capacity (MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in April'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark | [5 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total NER Wind |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | SJVN Solar |  | Solar | NER | 70 |  | 70 | Solar | 70 | 31.01.2026 | 70 | 03.02.2026 | 70 | 0 | [12 empty] | 0
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total NER Solar |  |  |  |  | 70 |  | 70 | 0 | 70 | 0 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total NER BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total NER Hybrid |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
| Total NER Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
1 | 1 | Subansiri Lower HEP | - | Hydro | NER | 2000 | 2000 | 1000 | Hydro | 750 | Unit-2: 02.12.2025 Unit-3: 21.01.2026 Unit-1: 31.01.2026 | 750 | Unit-2: 20.12.2025 Unit-3: 30.01.2026 Unit-1: 09.03.2026 | 750 | Unit-2: 23.12.2025 Unit-3: 01.02.2026 Unit-1: 20.03.2026 | Unit-4: 29.04.2026 | 250 |  |  | 250 | Unit-4 FTC application under process |  |  | 250 | 0 |  |  | 0
2 | [27 empty] | 1
3 | [27 empty] | 1
2 |  | 0 | 0 | 0 | NER | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  |  | 0 | [7 empty] | 1
5 | [27 empty] | 1
6 | [27 empty] | 1
7 | [27 empty] | 1
8 | [27 empty] | 1
1
| Total NER Hydro |  |  |  |  | 2000 |  | 1000 | 0 | 750 | 0 | 750 | 0 | 750 | 0 | 0 | 250 | 0 | 0 | 250 | [7 empty] | 0
1 | #N/A | [26 empty] | 1
2 | [27 empty] | 1
3 | [27 empty] | 1
4 | [27 empty] | 1
| Total NER PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1
| Total NER |  |  |  |  | 2070 |  | 1070 | 0 | 820 | 0 | 820 | 0 | 820 | 0 | 0 | 250 | 0 | 0 | 250 | [7 empty] | 0
COMPARISON
[5 empty] | NR | 0 |  |  |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | WR | 0 |  |  |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | SR | 0 |  |  |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | ER | 0 |  |  |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | NER | -70 |  |  |  | -70 |  | -70 |  | -70 | [5 empty] | 0

## Source wise
Wind Generation Capacity Details Under FTC/TOC/COD
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Installed Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in April'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | Test | Check
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total NR Wind |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | 2 | ASEJ6PL Khavda PSS8 | KPS3 | Wind | WR | 62.4 | 62.4 | 62.4 | Wind | 62.4 | 2026-03-06 | 62.4 | 2026-03-28 | 62.4 | 2026-03-28 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
2 | 9 | AGE26AL - SRPL Khavda PSS12 | KPS3 | Wind | WR | 140.4 | 137.5 | 140.4 | Wind | 140.4 | 2026-03-12 | 140.4 | 2026-03-20 | 137.5 | 2026-03-22 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.9 |  | 0 | 2.9 | 0 | 2.9
3 | 11 | Renew Green MHS One Pvt Ltd - RGESPL PSS-1 | Solapur | Wind | WR | 181.5 | 181.5 | 181.5 | Wind | 161.7 | 2026-03-06 | 161.7 | 2026-03-26 | 161.7 | 2026-03-27 |  | 19.8 | 0 | 0 | 19.8 |  |  | 0 |  | 19.8 | 0 | 0 | 0
4 | 13 | Veh Saurya Urja Pvt Ltd | Pachora | Wind | WR | 163.2 | 81.9 | 81.9 | Wind | 81.9 | 2026-02-23 | 69.3 | 2026-03-25 | 69.3 | 2026-03-26 |  | 0 | 0 | 0 | 0 |  |  | -93.9 |  | 0 | 0 | 0 | 93.9
5 | 15 | Juniper Green Energy Limited | Jam Khambhaliya | Wind | WR | 300 | 100 | 0 | Wind | 0 | [6 empty] | 0 |  | 0 | 100 | Wind FTC application yet to be submitted | PSS FTC - protection coordination pending from site, hence protection consent is remaining | -200 |  | 0 | 0 | 0 | 200
6 | 16 | Sprng Akshay Urja Pvt Ltd | Rajgarh | Wind | WR | 167.2 | 165 | 165 | Wind | 165 | 2026-01-13 | 165 | 2026-04-08 | 162.7 | 100: 29-12-2025 16.5: 31-12-2025 6.6: 05-01-2026 6.6: 28-01-2026 13.2: 30-01-2026 6.6: 04-02-2026 9.9: 18-02-2026 3.3: 10-04-2026 |  | 0 | 0 | 2.3 | 3.3 |  |  | -1.2 |  | 0 | 2.3 | 0 | 1.2
7 | 22 | NTPC REL Vanki | Bhuj | Wind | WR | 165 | 0 | 116.55 | Wind | 50.4 | 2026-04-20 | [5 empty] | 66.15 |  | 0 | 50.4 |  | Combined with lead generator Ayana | -114.6 |  | 66.15 | 0 | 0 | 114.6
8 | 28 | Serentica Renewables India4 Pvt Ltd | Kallam | Wind | WR | 350 | 250 | 66 | Wind | 66 | 2026-03-31 | [5 empty] | 0 | 66 | 0 | 66 |  |  | -284 |  | 0 | 0 | 0 | 284
9 | 30 | Oyster Green Hybrid One Pvt Ltd at Dayapar | Bhuj | Wind | WR | 99 | 99 | 0 | Wind | [7 empty] | 0 |  | 0 | 0 |  | FTC application yet to be submitted for Wind - proposed in April | -99 |  | 0 | 0 | 0 | 99
10 | 32 | AGE25CL Khavda PSS14 | KPS3 | Wind | WR | 67.6 | 65 | 67.6 | Wind | 67.6 | 2026-03-25 | 67.6 | 2026-03-28 | 65 | 2026-03-28 |  | 0 | 0 | 0 | 0 |  | Full COD complete | -2.6 |  | 0 | 2.6 | 0 | 2.6
11 | 33 | AGE26AL Khavda PSS14 | KPS3 | Wind | WR | 208 | 208 | 130 | Wind | 130 | 2026-04-13 | 67.6 | 2026-04-22 | 67.6 | 2026-04-22 |  | 0 |  | 0 | 130 |  |  | -10.4 |  | 0 | 0 | 0 | 10.4
12 | 34 | NTPC REL at Jamjodhpur | Jam Khambhaliya | Wind | WR | 630 | 0 | 53.55 | Wind | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received |  | -630 |  | 53.55 | 0 | 0 | 630
13 | 36 | Continuum Power Trading (TN) Private Limited | Bhuj | Wind | WR | 36 | 36 | 0 | Wind | [7 empty] | 0 |  | 0 | 36 |  | FTC application yet to be submitted for Wind - proposed in April | 0 |  | 0 | 0 | 0 | 0
14 | 39 | Sprng Vayu Vidyut Pvt Ltd | Rajgarh | Wind | WR | 198 | 0 | 0 | Wind | [10 empty] | 105 | CAT-2 yet to be received | [5 empty] | 0 | 93
15 | [26 empty] | 1 | 0
14 | [26 empty] | 1 | 0
15 | [26 empty] | 1 | 0
16 | [26 empty] | 1 | 0
17 | [26 empty] | 1 | 0
| Total WR Wind |  |  |  |  | 2768.3 | 1386.3 | 1064.9 | 0 | 925.4 |  | 734 |  | 726.2 |  | 0 | 85.95 | 66 | 2.3 | 510.5 | [6 empty] | 0 | 1531.6
1 | 2 | Sembcorp Green Infra Pvt. Ltd. | Gadag | Wind | SR | 300 | 262 | 109.2 | Wind | 109.2 | 01-09-2025 , 13-02-2026 , 11-02-2026 | 69.3 |  | 69.3 | 17-01-2025 |  | 0 | 39.9 | 0 | 39.9 |  | ToC for 14.7 MW issued on 23.03.26 |  | 0 | 0 |  | 0 | 190.8
2 | 3 | JSW Renew Energy Limited | Karur | Wind | SR | 189 | 150 | 189 | Wind | 189 | 17-09-2025 | 162 |  | 162 | 09.05.25 (32.4MW) 28.03.25 (43.2 MW) 27.03.25 (27 MW) 28.02.25 (59.4 MW) |  | 0 |  | 0 |  |  | Remaining 10 WTG's of 2.7 MW Plant PPC Report to be submitted by Developer but period for infirm injection i.e., 45 days plus 3 months expired . M/s JSW has to approach commission for infirm injection approval. |  | 0 | 0 |  | 0 | 27
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
| Total SR Wind |  |  |  |  | 489 | 412 | 298.2 | 0 | 298.2 |  | 231.3 |  | 231.3 |  | 0 | 0 | 39.9 | 0 | 39.9 | [6 empty] | 0 | 217.8
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total ER Wind |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total NER Wind |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India Wind |  |  |  |  | 3257.3 | 1798.3 | 1363.1 | 0 | 1223.6 |  | 965.3 |  | 957.5 |  | 0 | 85.95 | 105.9 | 2.3 | 550.4 | [6 empty] | 0 | 1749.4
Solar Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in April'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | 1 | IB VOGT SOLAR SEVEN PRIVATE LIMITED(IBVSSPL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.03.2026 18.03.2026 | 200 | 27.03.2026 | 200 | 150MW (30.03.2026) 50MW (01.04.2026) |  | 0 | 0 | 0 | 100 | [5 empty] | 0 | 0 | 0
2 | 2 | RENEW SAMIR SHAKTI THREE PRIVATE LIMITED | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 13.02.2026 16.02.2026 | 300 | 210.31MW dated17.03.2026 64.67MW dated 24.03.2026 25.02 MW 31.03.2026 | 300 | 210.31MW dated 17.03.2026 64.67MW dated 26.03.2026 |  | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0
3 | 3 | RENEW SOLAR SHAKTI THREE PRIVATE LIMITED(RSS3PL) | Fatehgarh-III | Solar | NR | 300 | 300 | 300 | SOLAR | 300 | 2026-11-02 | 300 | 2026-11-03 | 300 | 2026-03-13 |  | 0 |  | 0 | 0 | [5 empty] | 0 | 0 | 0
4 | 4 | ADANI SOLAR ENERGY BARMER ONE LIMITED(ASEB1L)) | Fatehgarh-III | Solar | NR | 600 | 600 | 251 | SOLAR | 251 | 2026-03-15 | 251 | 23-03-2026 | 251 | 25.03.2025 |  | 0 | 0 | 0 | 0 | [5 empty] | 349 | 0 | 349
5 | 5 | Khaba Renewable Energy Private Limited (KREPL) | Fatehgarh-III | Solar | NR | 250 | 250 | 221 | SOLAR | 221 | 2026-02-03 | 150 | 100MW on 13-03-26 50 MW on 27-03-2026 | 150 | 100MW-14 Mar 26 50MW-27 Mar 26 |  | 0 | 0 | 0 | 71 | [5 empty] | 29 | 0 | 29
6 | 7 | PROJECT ELEVEN RENEWABLE POWER PRIVATE LIMITED(P11RPPL) | Bhadla-II | Solar | NR | 150 | 150 | 100 | SOLAR | 100 | 25-03-2026 | 87.5 | 17.04.2025 | 87.5 | 21.04.2026 |  | 0 |  | 0 | 62.5 | [5 empty] | 0 | 0 | 0
7 | 8 | PROJECT 16 RENEWABLE POWER PRIVATE LIMITED(P16RPPL) | Bhadla-II | Solar | NR | 300 | 300 | 200 | SOLAR | 200 | 25-03-2026 | 150 | 16.04.2026 | 150 | 18.04.2026 |  | 0 |  | 0 | 50 | [5 empty] | 100 | 0 | 100
8 | 12 | Clean Max Celestial Private Limited(CMCPL) | Bikaner-II | Solar | NR | 250 | 250 | 234.57 | SOLAR | 0 | NA | [5 empty] | 234.57 |  | 0 | 250 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 0 | 0
9 | 13 | Clean Max Enviro Energy Solutions Limited(CMEESL) | Bikaner-II | Solar | NR | 100 | 100 | 93.75 | SOLAR | 0 | NA | [5 empty] | 93.75 |  | 0 | 100 |  | Annex. B Returned on 18.03.2026. Revised submitted on 30-03-26 |  |  |  | 0 | 0 | 0
10 | 14 | Energizent POWER Private Limited | Fatehgarh-III | Solar | NR | 250 | 250 | 129.6 | SOLAR | 129.6 | 60.6 MW on 27-03-2026 69 MW on 29-10-2025 | 69 | 2025-07-11 | 69 | 2025-09-11 |  | 0 |  | 0 | 60.6 | [5 empty] | 120.4 | 0 | 120.4
11 | 15 | BBMB Panipat | Panipat | Solar | NR | 10 | 8.8 | 8.8 | SOLAR | 8.8 | 2026-02-03 | 8.8 | 2026-11-03 | 8.8 | 2026-11-03 |  | 0 |  | 0 | 0 | [5 empty] | 1.2 | 0 | 1.2
12 | 17 | Adani Green Energy Twenty Five B Limited (AGE25BL) | Ramgarh-II | Solar | NR | 500 | 500 | 137.5 | SOLAR | 137.5 | 23-03-2026 | 137.5 | 28-03-2026 | 137.5 | 30-03-2026 |  | 0 |  | 0 | 362.5 | [5 empty] | 0 | 0 | 0
13 | 18 | Teq Green POWER XVIII Private Limited | Fatehgarh-III | Solar | NR | 50 | 50 | 0 | SOLAR | 0 | [6 empty] | 0 |  | 0 | 50 |  | FTC yet to apply for FTC |  |  |  | 0 | 0 | 0
14 | 19 | Renew Solar Shakti Five Private Limited | Fatehgarh-III | Solar | NR | 400 | 400 | 400 | SOLAR | 400 | 200MW on 25-03-2026 200MW on 28-03-2026 | [5 empty] | 0 |  | 0 | 400 |  | Annexure B returb 24.03.26 |  |  |  | 0 | 0 | 0
15 | 21 | HRP Green POWER Private Limited | Bhadla-III | Solar | NR | 300 | 296 | 0 | SOLAR | 296 | 2026-01-04 | 148 | 13.04.2026 | 148 | 148MW 13.04.2026 |  | 0 |  | 0 | 148 | [5 empty] | 4 | 0 | 4
16 | [26 empty] | 1 | 0
17 | [26 empty] | 1 | 0
18 | [26 empty] | 1 | 0
19 | [26 empty] | 1 | 0
20 | [26 empty] | 1 | 0
| Total NR Solar |  |  |  |  | 4060 | 4054.8 | 2676.22 | 0 | 2643.9 |  | 1801.8 |  | 1801.8 |  | 0 | 328.32 | 0 | 0 | 1654.6 | [6 empty] | 0 | 603.6
1 | 1 | AGE26AL Khavda PSS6 | KPS1 | Solar | WR | 750 | 750 | 750 | Solar | 750 | 2026-04-14 | 750 | 2026-04-20 | 750 | 50: 25-01-2026 250: 15-03-2026 50: 21-03-2026 50: 29-03-2026 50: 16-04-2026 58: 01-04-2026 242: 20-04-2026 |  | 0 | 0 | 0 | 0 | CEA EI approval yet to be received | Full COD complete | 0 |  | 0 | 0 | 0 | 0
2 | 3 | AGE25CL Khavda PSS8 | KPS3 | Solar | WR | 500 | 500 | 500 | Solar | 500 | 2026-03-27 | 375 | 2026-03-30 | 350 | 2026-03-30 |  | 0 | 125 | 25 | 150 |  |  | 0 |  | 0 | 25 | 0 | 0
3 | 4 | AGE24L SRPL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-03-13 | 100 | 2026-03-25 | 100 | 2026-03-26 |  | 0 | 50 | 0 | 50 |  |  | 0 |  | 0 | 0 | 0 | 0
4 | 5 | AGE24L Khavda PSS5 | KPS1 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-02-16 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
5 | 6 | AGE26BL Khavda PSS10 | KPS3 | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-02-16 | 150 | 2026-03-17 | 150 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
6 | 12 | Avaada GJ Sustainable Private Limited | Lakadiya | Solar | WR | 200 | 200 | 200 | Solar | 200 | 2026-03-24 | 200 | 2026-04-07 | 200 | 108.33: 07-02-2026 91.67: 11-04-2026 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
7 | 19 | Ayana Power Four Private Limited at Zura | Bhuj | Solar | WR | 150 | 150 | 150 | Solar | 150 | 2026-03-17 | 150 | 2026-03-31 | 150 | 2026-03-31 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
8 | 20 | NTPC REL Khavda PSS2 | KPS2 | Solar | WR | 1555 | 1555 | 1555 | Solar | 1555 | 2026-03-23 | 1555 | 2026-03-30 | 1555 | 2026-03-30 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
9 | 21 | NTPC REL Khavda PSS1 | KPS3 | Solar | WR | 1200 | 1095 | 1200 | Solar | 1095 | 2026-04-11 | 1005 | 2026-03-30 | 1005 | 2026-03-30 |  | 105 | 90 | 0 | 195 | CONN-TD-4 remaining for 105 MW |  | 0 |  | 105 | 0 | 0 | 0
10 | 23 | Coal India Limited at GIPCL | KPS2 | Solar | WR | 300 | 0 | 300 | Solar | 0 | [6 empty] | 300 |  | 0 | 0 | CAT-2 yet to be received | POWER park developer GIPCL - proposed in April | -300 |  | 300 | 0 | 0 | 300
11 | 24 | NTPC REL at GSECL | KPS2 | Solar | WR | 265 | 0 | 64.76 | Solar | 64.76 | 2026-04-21 | [5 empty] | 0 |  | 0 | 64.76 |  | POWER park developer GSECL | -200.24 |  | 0 | 0 | 0 | 200.24
12 | 25 | Engie Energy India Pvt Ltd at GSECL | KPS2 | Solar | WR | 200 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 200 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS - proposed in April | 0 |  | 0 | 0 | 0 | 0
13 | 26 | JSW Renew Energy Ten Ltd at GSECL | KPS2 | Solar | WR | 300 | 0 | 0 | Solar | [7 empty] | 0 |  | 0 | 300 | CAT-2 yet to be received | POWER park developer GSECL, charging proposed through interim connection from South block GSECL PSS already commuincated through mail for submission of FTC application but it is stiil not received as on 27.03.26 | 0 |  | 0 | 0 | 0 | 0
14 | 38 | Waree Energies Limited | Rewa | Solar | WR | 170 | 0 | 170 | Solar | [10 empty] | 170 | CAT-2 yet to be received | [5 empty] | 0 | 0
15 | [26 empty] | 1 | 0
16 | [26 empty] | 1 | 0
| Total WR Solar |  |  |  |  | 6040 | 4700 | 5339.76 | 0 | 4764.76 |  | 4435 |  | 4410 |  | 0 | 405 | 265 | 25 | 1129.76 | [6 empty] | 0 | 500.24
1 | 1 | SAEL Solar MHP2 Pvt Ltd | Kurnool-III | Solar | SR | 359.7 | 300 | 359.7 | Solar | 359.7 | 26-02-2026 | 359.7 | 13-03-2026 | 300 (359.7) | 09-01-2026 (156.88 MW) , 23-02-2026 ( 66.06 MW) , 13-03-2026 (77.06 MW) |  | 0 |  | 0 |  |  | Total plant commissioned |  | 0 | #VALUE! |  | 0 | #VALUE!
2 | 7 | TP Saurya Limited | Koppal | Solar | SR | 352 | 300 | 281.6 | Solar | 281.6 | 23-03-2026 | 281.6 | 52.8MW: 17.04.26 | 238.46 (281.6) | 08-01-2026 ( 130.77 MW), 03-02-2026 (61.54 MW), 18-04-2026 (46.15MW) |  | 0 | 0 | 0 | 52.8 |  |  |  | 0 | #VALUE! |  | 0 | #VALUE!
3 | 8 | NTPC Ramagundam (176MW) | Ramagundam | Solar | SR | 204.6 | 176 | 154.8 | Solar | 154.8 | 27-03-2026 |  |  |  | Trial run on 20.04.26 |  | 0 | 154.8 | 0 | 154.8 | [6 empty] | 0 | 49.8
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
| Total SR Solar |  |  |  |  | 916.3 | 776 | 796.1 | 0 | 796.1 |  | 641.3 |  | 0 |  | 0 | 0 | 154.8 | 0 | 207.6 | [6 empty] | 0 | 708.7
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total ER BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total NER Solar |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India Solar |  |  |  |  | 11016.3 | 9530.8 | 8812.08 | 0 | 8204.76 |  | 6878.1 |  | 6211.8 |  | 0 | 733.32 | 419.8 | 25 | 2991.96 | [6 empty] | 0 | 1812.54
BESS Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in april'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | 9 | ACME SUN POWER PRIVATE LIMITED(ASPPL) | Bhadla-II | BESS | NR | 300 | 300 | 166.665 | BESS | 166.665 | 66.66 FTC completed on 26-02-2026. 33.33 MW 17 MAR 26 66.66MW 24-03-2026 33.33MW | 166.665 | 33.335 MW 06-03-2026 33.335 MW 12-03-2026 33.33MW- 31.03.2026 33.33MW- 01.04.2026 33.334MW-06.04.2026 | 166.665 | 33.335 MW on 08-03-2026 33.335 MW on 14-03-2026 33.333 MW on 02-04-2026 33.333 MW on 03-04-2026 33.334 MWon 08-04-2026 |  | 0 |  | 0 | 133 | [5 empty] | 0.335 | 0 | 0.335
2 | 10 | ACME SURYODAYA PRIVATE LIMITED(ACME_SPL) | Fatehgarh-I | BESS | NR | 300 | 285 | 285 | BESS | 285 | 76 MW FTC completed on 10-02-2026. 95 MW FTC APPROVED 14 MAR 2026 114 MW FTC issued on 29-03-2026 | 285 | 19 MW 25-02-2026 38 MW 03-03-2026 19 MW11-03-2026 95MW-23.03.2026 76MW-06.04.2026 | 285 | 19 MW on 27-02-2026 38 MW on 05-03-2026 19 MW on 13-03-2026 95 MW on 25-03-2026 76 MW on 08-04-2026 38MW on 13-04-2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 15 | 0 | 15
3 | 11 | ACME Surya POWER Private Limited (ASRPPL) | Bikaner-II | BESS | NR | 250 | 250 | 142.857 | BESS | 142.857 | 16-03-2026 (71.43MW) 17-03-2026 (35.71MW) 24-03-2026 (35.71MW) | 139.509 | 23-03-2026 (60MW) 24-03-2026 (35.71MW) 29-03-2026 (11.429MW) | 139.509 | 60MW dated 23.03.26 35.714 dated 24-03-26 11.429 MW on 29-03-26 32.366MW on 13-04-26 |  | 0 | 0 | 0 | 110.491 | [5 empty] | 1.4211e-14 | 0 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
| Total NR BESS |  |  |  |  | 850 | 835 | 594.522 | 0 | 594.522 |  | 591.174 |  | 591.174 |  | 0 | 0 | 0 | 0 | 243.491 | [6 empty] | 0 | 15.335
1 | 8 | ARE43L BESS - SRPL Khavda PSS10 | KPS3 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 2026-03-16 | 400 | 2026-04-15 | 400 | 80: 11-03-2026 80: 20-03-2026 60: 28-03-2026 120: 30-03-2026 20: 02-04-2026 20: 11-04-2026 20: 15-04-2026 |  | 80 | 0 | 0 | 75 |  |  | 0 |  | 80 | 0 | 0 | 0
2 | 10 | ARE37L BESS - AGEL Khavda PSS5 | KPS1 | BESS | WR | 475 | 475 | 480 | BESS | 400 | 2026-04-10 | 320 | 2026-04-17 | 320 | 80: 01-04-2026 80: 01-04-2026 80: 11-04-2026 60: 15-04-2026 20: 17-04-2026 |  | 80 | 80 | 0 | 155 |  |  | 0 |  | 80 | 0 | 0 | 0
3 | 31 | ARE36L BESS - AGEL Khavda PSS8 | KPS3 | BESS | WR | 316 | 284 | 320 | BESS | 280 | 2026-04-24 | 80 | 2026-04-23 | 80 | 2026-04-24 |  | 40 | 200 | 0 | 160 |  |  | -76 |  | 40 | 0 | 0 | 76
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
7 | [26 empty] | 1 | 0
| Total WR BESS |  |  |  |  | 1266 | 1234 | 1280 | 0 | 1080 |  | 800 |  | 800 |  | 0 | 200 | 280 | 0 | 390 | [6 empty] | 0 | 76
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total SR BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total ER BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total NER BESS |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India BESS |  |  |  |  | 2116 | 2069 | 1874.522 | 0 | 1674.522 |  | 1391.174 |  | 1391.174 |  | 0 | 200 | 280 | 0 | 633.491 | [6 empty] | 0 | 91.335
Hybrid Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in april'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | 6 | Juniper Green Stellar Private Limited(JGSPL) | Fatehgarh-IV | Hybrid_(285MW Solar, 250MW Wind, 180MW BESS) | NR | 715 | 365 | 365 | SOLAR+BESS | 465 | Solar:16.03.2026 (185MW) 06.04.2026 (100MW) BESS: 17.03.2026 (90MW) 21.03.2026 (90 MW) | 365 | 88MW solar-25.03.26 90MW-BESS 02-04-2026 10.04.2026 (97 MW Solar) 90MW BESS 22.04.2026 | 365 | 27 Mar 26-88MW solar 12.04.26 97MW Solar 90MW BESS-08.04.2026 90MW BESS 24.04.2026 |  | 0 | 0 | 0 | 187 |  | Capacity(MW) applied for FTC_ Solar- 185 BESS-180 | TOC Isuued capcity: 88-solar 90MW-BESS | COD Declared capcity: 88-solar 90MW-BESS | Capacity(MW) commisioning expected in Apr'26: (187)solar-97 Bess-90 | 163 | 0 | 163
2 | 20 | AMPIN ENERGY GREEN TEN PRIVATE LIMITED(AEG10PL) | Fatehgarh-IV | HYBRID 120 (114.4 MW Solar + 40.95 MW Wind) | NR | 155 | 120 | 155 | solar+Wind | 155 | 2026-12-02 | 155 | 27.03.2026 | 155 | 114.4MW--04.04.2026 40.4MW- 04.04.2026 |  | 0 |  |  |  |  | TOC Isuued capcity: 120(solar-114.4+wind-40.4) |  |  |  | 0 | 0 | 0
3 | 22 | Aditya Birla Renewables subsdiary Ltd | Fatehgarh-III | Hybrid_(292MVA Solar, 287MVA Wind) | NR | 608 not applied | 608 not applied | 0 | Solar+Wind | 0 | [6 empty] | 0 |  | 0 | 608 not applied | Hybrid_(292MVA Solar, 287MVA Wind) | Registration and Conn6 pending |  |  |  | #VALUE! | 0 | #VALUE!
4 | [26 empty] | 1
5 | [26 empty] | 1 | 0
| Total NR Hybrid |  |  |  |  | 870 | 485 | 520 | 0 | 620 | 46358 | 520 | 0 | 520 |  | 0 | 0 | 0 | 0 | 187 | 0 | [5 empty] | 0 | 163
1 | 7 | AGE26BL Khavda PSS10 | KPS3 | Hybrid (Solar + Wind) | WR | 298 | 216 | 298 | Hybrid | 298 | 2026-03-09 | 298 | 2026-03-17 | 298 | 2026-03-20 |  | 0 | 0 | 0 | 0 |  | Hybrid connectivity 216 MW Full COD complete | 0 |  | 0 | 0 | 0 | 0
2 | 14 | Oyster Green Hybrid One Pvt Ltd | Pachora | Hybrid (Solar + Wind) | WR | 181 | 67 | 52.8 | Solar | 52.8 | 2026-02-25 | 52.8 | 2026-03-25 | 52.8 | 2026-03-26 |  | 0 | 0 | 0 | 0 |  |  | -128.2 |  | 0 | 0 | 0 | 128.2
3 | 17 | TEQ Green Power XI Pvt Ltd | Kallam | Hybrid (Solar + Wind) | WR | 204.1 | 150.3 | 201 | Hybrid | 174 | 2026-04-22 | 160.225 | 2026-04-01 | 160.225 | Wind: 18.9: 30-06-2025 32.4: 30-06-2025 13.5: 16-08-2025 13.5: 02-10-2025 2.7: 07-11-2025 5.4: 29-11-2025 10.8: 20-12-2025 16.2: 03-04-2026 Solar: 24.425: 16-08-2025 22.4: 11-01-2026 |  | 27 | 0 | 0 | 40.775 |  |  | -3.1 |  | 27 | 0 | 0 | 3.1
4 | 18 | Ayana Power Four Private Limited at Devasar | Bhuj | Hybrid (Solar + Wind) | WR | 129.9 | 100 | 129.9 | Hybrid | 129.9 | 2025-07-10 | 129.9 | 2026-03-31 | 129.9 | 2026-03-31 |  | 0 | 0 | 0 | 0 |  | Full COD complete | 0 |  | 0 | 0 | 0 | 0
5 | 27 | Mounting Renewable Power Ltd | Jam Khambhaliya | Hybrid (Solar + Wind) | WR | 250 | 0 | 128.7 | Hybrid | [7 empty] | 128.7 | 0 | 0 | 128.7 | CAT-2 yet to be received |  | -121.3 |  | 128.7 | 0 | 0 | 121.3
6 | 29 | Airpower Windfarms Pvt Ltd | Jam Khambhaliya | Hybrid (Solar + Wind+BESS) | WR | 229 | 140 | 81.25 | Hybrid | [7 empty] | 0 |  | 0 | 50 |  |  | -179 |  | 81.25 | 0 | 0 | 179
7 | 35 | Veh Jayin Renewables Private Limited | Rajgarh | Hybrid (Solar + Wind) | WR | 196.8 | 0 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in April | -196.8 |  | 0 | 0 | 0 | 196.8
8 | 37 | Aditya Birla Renewable Energy Limited (ABREL) Valsara | Bhuj-II | Hybrid (Solar + Wind) | WR | 314 | 294 | 0 | Hybrid | [7 empty] | 0 |  | 0 | 0 | CONN-TD-4 signed, CAT-2 yet to be received | FTC application yet to be submitted for PSS, Wind, Solar - proposed in May | -314 |  | 0 | 0 | 0 | 314
9 | [26 empty] | 1 | 0
| Total WR Hybrid |  |  |  |  | 1802.8 | 967.3 | 891.65 | 0 | 654.7 |  | 640.925 |  | 640.925 |  | 0 | 155.7 | 0 | 0 | 219.475 | [6 empty] | 0 | 942.4
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
7 | [26 empty] | 1 | 0
| Total SR Hybrid |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total ER Hybrid |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total NER Hybrid |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India Hybrid |  |  |  |  | 2672.8 | 1452.3 | 1411.65 | 0 | 1274.7 |  | 1160.925 |  | 1160.925 |  | 0 | 155.7 | 0 | 0 | 406.475 | [6 empty] | 0 | 1105.4
Coal Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in april'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | 23 | Ghatampur TPS | Ghatampur | Thermal | NR | 660 | 660 | 660 | Thermal | 660 | 30-03-2026 | [5 empty] | 660 |  |  | 660 | [5 empty] | 0 | 0 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
| Total NR Coal |  |  |  |  | 660 | 660 | 660 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 660 | [6 empty] | 0 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total WR Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total SR Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | 1 | PVUNL Unit-2 | - | Coal | ER | 2400 | 2400 | 2400 | Coal | 1600 | - | 800 | - | 800 | - | - | 800 | 800 | 0 | 800 | SPS has been implemented as per the undertaking submitted. | Format-IV has been issued on 16.03.2026. Trial operation of Unit #2 (800 MW) of Patratu STPP Phase-I (3×800 MW) is tentatively expected from 13.04.2026. |  |  |  | 800 | 0 | 800
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
7 | [26 empty] | 1 | 0
| Total ER Coal |  |  |  |  | 2400 | 2400 | 2400 | 0 | 1600 |  | 800 |  | 800 |  | 0 | 800 | 800 | 0 | 800 | [6 empty] | 0 | 800
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total NER Coal |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India Coal |  |  |  |  | 3060 | 3060 | 3060 | 0 | 2260 |  | 800 |  | 800 |  | 0 | 1460 | 800 | 0 | 1460 | [6 empty] | 0 | 800
Hydro Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity(MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in April'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total NR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total WR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total SR Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total ER Hydro |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | 1 | Subansiri Lower HEP | - | Hydro | NER | 2000 | 2000 | 1000 | Hydro | 750 | Unit-2: 02.12.2025 Unit-3: 21.01.2026 Unit-1: 31.01.2026 | 750 | Unit-2: 20.12.2025 Unit-3: 30.01.2026 Unit-1: 09.03.2026 | 750 | Unit-2: 23.12.2025 Unit-3: 01.02.2026 Unit-1: 20.03.2026 | Unit-4: 29.04.2026 | 250 |  |  | 250 | Unit-4 FTC application under process |  |  | 250 | 0 |  | 0 | 1000
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
| Total NER Hydro |  |  |  |  | 2000 | 2000 | 1000 | 0 | 750 |  | 750 |  | 750 |  | 0 | 250 | 0 | 0 | 250 | [6 empty] | 0 | 1000
| All India Hydro |  |  |  |  | 2000 | 2000 | 1000 | 0 | 750 |  | 750 |  | 750 |  | 0 | 250 | 0 | 0 | 250 | [6 empty] | 0 | 1000
PSP Generation Capacity Details Under FTC/TOC/COD | [26 empty] | 0 | 0
Sr. No |  | Generating Station | Pooling Station | Plant Type | Region | Total Capacity(MW) | Total Capacity(MW) (For which CONTD4 issued) | Capacity(MW) applied for FTC | Sources Type Applied for FTC(Wind/Solar/BESS/Coal/Hydro/PSP) | FTC Approved Capacity(MW) | FTC date if completed | TOC Issued Capacity(MW) | TOC issuance date if Completed | COD declared Capacity (MW) | COD Date if Declared | Proposed FTC date if Under process | Capacity Under Process for FTC | Capacity Under Process for TOC | Capacity Pending for COD | Capacity(MW) commisioning expected in April'26 | Issues if any causing delay in FTC/TOC/COD | Any Otherremark |  |  |  |  | 0 | #VALUE!
1 | 16 | Tehri | - | Pump Storage | NR | 1000 | 1000 | 1000 | PSP HYDRO | 1000 | 2026-06-03 | 1000 | 250 MW U#4 on 10.04.2026 | 1000 | 12.04.2026 |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
5 | [26 empty] | 1 | 0
6 | [26 empty] | 1 | 0
| Total NR PSP |  |  |  |  | 1000 | 1000 | 1000 | 0 | 1000 |  | 1000 |  | 1000 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total WR PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total SR PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
| Total ER PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
1 | #N/A | [25 empty] | 1 | 0
2 | [26 empty] | 1 | 0
3 | [26 empty] | 1 | 0
4 | [26 empty] | 1 | 0
| Total NER PSP |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1 | 0
| All India PSP |  |  |  |  | 1000 | 1000 | 1000 | 0 | 1000 |  | 1000 |  | 1000 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0
COMPARISON
[5 empty] | Wind | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | Solar | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | BESS | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | Hybrid | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | Coal | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
[5 empty] | Hydro | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0
PSP